## QuestData
Yes
No
N/A
# | Question | ANS | CMRL | Comments | Thread | Sub
1 | Is the Technology Readiness at TRL 1 or greater? |  | 1 |  |  | Technology Maturity
2 | Is the Technology Readiness at TRL 2 or greater? |  | 2 |  |  | Technology Maturity
3 | Is the Technology Readiness at TRL 3 or greater? |  | 3 |  |  | Technology Maturity
4 | Is the Technology Readiness at TRL 4 or greater? |  | 4 |  |  | Technology Maturity
5 | Is the Technology Readiness at TRL 5 or greater? |  | 5 |  |  | Technology Maturity
6 | Is the Technology Readiness at TRL 6 or greater? |  | 6 |  |  | Technology Maturity
7 | Is the Technology Readiness at TRL 7 or greater? |  | 7 |  |  | Technology Maturity
8 | Is the Technology Readiness at TRL 7 or greater? |  | 8 |  |  | Technology Maturity
9 | Is the Technology Readiness at TRL 9? |  | 9 |  |  | Technology Maturity
10 | Is the Technology Readiness at TRL 9? |  | 10 |  |  | Technology Maturity
11 | Have potential manufacturing sources been identified for technology capability needs (Understand state of the art)? |  | 3 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
12 | Have industrial base capabilities and gaps/risks been identified for key technologies, components, and/or key processes capabilities? |  | 4 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
13 | Has the industrial base capabilities assessment been initiated to identify potential manufacturing sources to produce the required capability? |  | 5 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
14 | Have sole/single/foreign source vendors and vendors of technologies with potential obsolescence issues been identified? |  | 5 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
15 | Has planning begun to minimize the risks associated with sole/single/foreign source vendors? |  | 5 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
16 | Has an industrial base capabilities assessment for MS B been completed? |  | 6 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
17 | Is the industrial capability in place to support the manufacturing of development articles or commodities? |  | 6 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
18 | Are the plans to minimize sole/single/foreign sources and obsolescence issues complete? |  | 6 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
19 | Has the need for sole/single/foreign sources been justified? |  | 6 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
20 | Have potential alternative sources been identified? |  | 6 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
21 | Has the industrial capability to support production been analyzed? |  | 7 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
22 | Is the stability of all sole/single/foreign sources and obsolescence issues being assessed/monitored? |  | 7 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
23 | Are the necessary alternates to sole/single/foreign sources being developed? |  | 7 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
24 | Has the industrial base capability assessment for Milestone C been completed? |  | 8 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
25 | Is the industrial capability in place to support Low Rate Initial Production (LRIP)? |  | 8 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
26 | Are all necessary sources available including multi-sourcing where cost-effective or necessary to mitigate risk? |  | 8 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
27 | Is the industrial capability in place to support the start of Full Rate Production (FRP)? |  | 9 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
28 | Does the industrial capability support Full Rate Production (FRP)? |  | 10 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
29 | Has the industrial capability been assessed to support modifications, upgrades, surge, and other potential manufacturing requirements? |  | 10 |  | A - Technology & Industrial Base | A.1 - Technology Transition to Production
30 | Have new manufacturing concepts and potential solutions been identified? |  | 2 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
31 | Have manufacturing technology concepts been identified through experiments/models? |  | 3 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
32 | Have pertinent Manufacturing Science (MS) and Advanced Manufacturing Technology requirements been identified? |  | 4 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
33 | Have the required manufacturing technology development efforts been initiated as applicable? |  | 5 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
34 | Are the necessary manufacturing technology development efforts continuing? |  | 6 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
35 | Have the required manufacturing technology development solutions been demonstrated in a production relevant environment? |  | 6 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
36 | Are the necessary manufacturing technology development efforts still continuing? |  | 7 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
37 | Have the required manufacturing science and manufacturing technology development solutions been demonstrated in a production representative environment? |  | 7 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
38 | Are the primary manufacturing technology efforts concluding and some improvement efforts continuing? |  | 8 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
39 | Have the required manufacturing technology development solutions been validated on a pilot line? |  | 8 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
40 | Have the required manufacturing technology process improvement efforts been initiated for Full Rate Production (FRP)? |  | 9 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
41 | Are manufacturing technology continuous process improvements ongoing? |  | 10 |  | A - Technology & Industrial Base | A.2 - Manufacturing Technology Development
42 | Have relevant materials/processes been evaluated for manufacturability using experiments/models? |  | 3 |  | B - Design | B.1 - Producibility Program
43 | Are initial producibility and manufacturability assessments of preferred systems capability or commodity concepts completed? |  | 4 |  | B - Design | B.1 - Producibility Program
44 | Are the results of the producibility and manufacturability assessment being considered in the selection of preferred design capability or commodity concepts? |  | 4 |  | B - Design | B.1 - Producibility Program
45 | Are the results of the producibility and manufacturability assessment being reflected in the Technology Development strategy for developing key components commodity or capability technologies? |  | 4 |  | B - Design | B.1 - Producibility Program
46 | Have producibility & manufacturability assessments of key technologies and components capabilities or commodities been initiated as appropriate? |  | 5 |  | B - Design | B.1 - Producibility Program
47 | Do ongoing design trades consider manufacturing processes and industrial base capability constraints? |  | 5 |  | B - Design | B.1 - Producibility Program
48 | Have the manufacturing processes been assessed for capability to test and verify in production and their influence on Operations and Support (O&S) identified requirements to support operational uses? |  | 5 |  | B - Design | B.1 - Producibility Program
49 | Have producibility assessments and producibility trade studies (performance vs. producibility) of key technologies/components capabilities and commodities been completed? |  | 6 |  | B - Design | B.1 - Producibility Program
50 | Are the results of the producibility assessments and trade studies being used to shape the Acquisition Strategy, Systems Engineering Plan (SEP), Manufacturing and Producibility plans, and Planning for Engineering and Manufacturing Development (EMD) or approach used for product development or technology insertion programs? |  | 6 |  | B - Design | B.1 - Producibility Program
51 | Are the preliminary capability or commodity design choices assessed against manufacturing processes and industrial base capability constraints? |  | 6 |  | B - Design | B.1 - Producibility Program
52 | Are the producibility enhancement efforts [e.g. Design For Mfg., Assembly, etc. (DFX)] initiated? |  | 6 |  | B - Design | B.1 - Producibility Program
53 | Are the detailed producibility trade studies using detailed knowledge of key capability or commodity design characteristics and related manufacturing process capabilities completed? |  | 7 |  | B - Design | B.1 - Producibility Program
54 | Are the producibility enhancement efforts (e.g. Design For Mfg., Assembly, etc.) ongoing for an optimized integrated system? |  | 7 |  | B - Design | B.1 - Producibility Program
55 | Are manufacturing processes re-assessed as changes or new requirements are made on the program for additional needed for capability to test and verify potential influence on Operations & Support? |  | 7 |  | B - Design | B.1 - Producibility Program
56 | Have the producibility improvements been implemented on the system? |  | 8 |  | B - Design | B.1 - Producibility Program
57 | Have the known producibility issues been resolved and pose no significant risk for Low Rate Initial Production (LRIP)? |  | 8 |  | B - Design | B.1 - Producibility Program
58 | Have prior producibility improvements been analyzed for effectiveness during Low Rate Initial Production (LRIP)? |  | 9 |  | B - Design | B.1 - Producibility Program
59 | Have the producibility issues/risks discovered in Low Rate Initial Production (LRIP) been mitigated and pose no significant risk for Full Rate Production (FRP)? |  | 9 |  | B - Design | B.1 - Producibility Program
60 | Have design producibility improvements been demonstrated in Full Rate Production (FRP)? |  | 10 |  | B - Design | B.1 - Producibility Program
61 | Are process producibility improvements ongoing? |  | 10 |  | B - Design | B.1 - Producibility Program
62 | Are all modifications, upgrades, Diminishing Mfg Sources & Material Shortages (DMSMS), and other changes assessed for producibility? |  | 10 |  | B - Design | B.1 - Producibility Program
63 | Have manufacturing research opportunities been identified? |  | 1 |  | B - Design | B.2 - Design Maturity
64 | Have potential applications been defined? |  | 2 |  | B - Design | B.2 - Design Maturity
65 | Have broad performance goals been identified that may drive manufacturing options? |  | 2 |  | B - Design | B.2 - Design Maturity
66 | Have top level performance requirements been defined for potential applications? |  | 3 |  | B - Design | B.2 - Design Maturity
67 | Have trade-offs in design options been assessed based on experiments? |  | 3 |  | B - Design | B.2 - Design Maturity
68 | Are product commodity lifecycle requirements and technical requirements being evaluated? |  | 3 |  | B - Design | B.2 - Design Maturity
69 | Do the Systems Engineering Plan (SEP) and the Test and Evaluation Strategy planning efforts recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle? |  | 4 |  | B - Design | B.2 - Design Maturity
70 | Have initial potential Key Performance Parameters (KPPs) been identified for the preferred systems capability or commodity concept? |  | 4 |  | B - Design | B.2 - Design Maturity
71 | Are system characteristics and measures to support required capabilities identified? |  | 4 |  | B - Design | B.2 - Design Maturity
72 | Are form, fit, and function constraints and manufacturing capabilities identified for the preferred systems capability or commodity concepts? |  | 4 |  | B - Design | B.2 - Design Maturity
73 | Are lower level performance requirements sufficient to proceed to the preliminary design? |  | 5 |  | B - Design | B.2 - Design Maturity
74 | Are all enabling/critical technologies and components identified? |  | 5 |  | B - Design | B.2 - Design Maturity
75 | Do enabling/critical technologies and components consider the product lifecycle? |  | 5 |  | B - Design | B.2 - Design Maturity
76 | Have the evaluation of design Key Characteristics (KC) been initiated? |  | 5 |  | B - Design | B.2 - Design Maturity
77 | Have product data required for prototype component capability or commodity manufacturing been released? |  | 5 |  | B - Design | B.2 - Design Maturity
78 | Has a system allocated baseline been established? |  | 6 |  | B - Design | B.2 - Design Maturity
79 | Are the product requirements and features well enough defined to support Preliminary Design Review? |  | 6 |  | B - Design | B.2 - Design Maturity
80 | Has product data essential for subsystem/system prototyping capability or commodity demonstration been released? |  | 6 |  | B - Design | B.2 - Design Maturity
81 | Have all enabling/critical technologies/components, capabilities or commodities been demonstrated? |  | 6 |  | B - Design | B.2 - Design Maturity
82 | Have preliminary design capability or commodity Key Characteristics (KC) been defined and are mitigation plans in development? |  | 6 |  | B - Design | B.2 - Design Maturity
83 | Are the product design and features well enough defined to support critical design review even though design change traffic may be significant? |  | 7 |  | B - Design | B.2 - Design Maturity
84 | Has all the product data essential for component capability or commodity manufacturing been released? |  | 7 |  | B - Design | B.2 - Design Maturity
85 | Have potential Key Characteristic risk issues been identified? |  | 7 |  | B - Design | B.2 - Design Maturity
86 | Have preliminary design capability or commodity Key Characteristic (KC) issues been defined and are mitigation plans in development? |  | 7 |  | B - Design | B.2 - Design Maturity
87 | Is the detailed design of product commodity or capability features and interfaces complete? |  | 8 |  | B - Design | B.2 - Design Maturity
88 | Has all the product data essential for system capability or commodity manufacturing been released? |  | 8 |  | B - Design | B.2 - Design Maturity
89 | Does the design change traffic have minimal impact on Low Rate Initial Production (LRIP)? |  | 8 |  | B - Design | B.2 - Design Maturity
90 | Are the Key Characteristics attainable based upon pilot line demonstrations? |  | 8 |  | B - Design | B.2 - Design Maturity
91 | Are the major product design features and configuration stable? |  | 9 |  | B - Design | B.2 - Design Maturity
92 | Has the system design capability or commodity been validated through operational testing of Low Rate Initial Production (LRIP) items? |  | 9 |  | B - Design | B.2 - Design Maturity
93 | Is the Physical Configuration Audit (PCA) or equivalent complete as necessary if applicable? |  | 9 |  | B - Design | B.2 - Design Maturity
94 | Is the design change traffic limited to minor configuration changes? |  | 9 |  | B - Design | B.2 - Design Maturity
95 | Are all Key Characteristics controlled in Low Rate Initial Production (LRIP) to appropriate quality levels? |  | 9 |  | B - Design | B.2 - Design Maturity
96 | Is the product design stable (i.e. design changes are few and generally limited to those required for continuous improvement or in reaction to obsolescence)? |  | 10 |  | B - Design | B.2 - Design Maturity
97 | Are all Key Characteristics controlled in Full Rate Production (FRP) to appropriate quality levels? |  | 10 |  | B - Design | B.2 - Design Maturity
98 | Has the cost model approach been identified for the defined capability or commodity? |  | 2 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
99 | Have initial cost targets and risks been identified for the defined capability or commodity? |  | 3 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
100 | Has a high level process chart model been developed for the defined capability or commodity? |  | 3 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
101 | Have technology cost models been developed for new process steps and materials based on experiments? |  | 3 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
102 | Have key manufacturing, material and specialized requirement cost drivers been identified? |  | 4 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
103 | Are detailed process chart cost models driven by process variables? |  | 4 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
104 | Has cost driver uncertainty been quantified? |  | 4 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
105 | Do prototype components or simulations produced in a production relevant environment drive the formulation of the final production cost model? |  | 5 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
106 | Is there a realistic cost model that includes materials, labor, equipment, tooling/Special Test Equipment (STE), setup, yield/scrap/rework, Work In Progress (WIP), and capability/capacity constraints? |  | 5 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
107 | Have cost models been updated with design requirements, material specifications, tolerances, integrated master schedule, results of system/subsystem simulations and production relevant prototype demonstrations? |  | 6 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
108 | Are cost models updated with the results of systems/sub-systems items produced in a production representative environment, production plant layout and design, and obsolescence solutions? |  | 7 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
109 | Have cost models been updated with results of the pilot line build? |  | 8 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
110 | Has the Full Rate Production (FRP) cost model been updated with the result of the Low Rate Initial Production (LRIP) build? |  | 9 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
111 | Has the cost model been validated against actual Full Rate Production (FRP) cost? |  | 10 |  | C - Cost & Funding | C.1 - Production Cost Knowledge (Cost modeling)
112 | Have manufacturing cost implications been identified? |  | 1 |  | C - Cost & Funding | C.2 - Cost Analysis
113 | Have cost elements been identified? |  | 2 |  | C - Cost & Funding | C.2 - Cost Analysis
114 | Has a sensitivity analysis been conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory)? |  | 3 |  | C - Cost & Funding | C.2 - Cost Analysis
115 | Have producibility cost risks been assessed? |  | 4 |  | C - Cost & Funding | C.2 - Cost Analysis
116 | Do initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR) the selection of your capability or commodity as the best approach? |  | 4 |  | C - Cost & Funding | C.2 - Cost Analysis
117 | Are costs analyzed using prototype component capability or commodity demonstration actuals to ensure target costs are achievable? |  | 5 |  | C - Cost & Funding | C.2 - Cost Analysis
118 | Are decisions regarding design choices, make/buy, capacity, process capability, sources, quality, key characteristics, yield/rate, and variability influenced by cost models? |  | 5 |  | C - Cost & Funding | C.2 - Cost Analysis
119 | Are costs analyzed using prototype system/sub-system demonstation capability or commodity actuals to ensure target costs are achievable? |  | 6 |  | C - Cost & Funding | C.2 - Cost Analysis
120 | Have cost targets been allocated to subsystems lower levels of the capability or commodity being developed? |  | 6 |  | C - Cost & Funding | C.2 - Cost Analysis
121 | Have cost reduction and avoidance strategies been developed? |  | 6 |  | C - Cost & Funding | C.2 - Cost Analysis
122 | Have the manufacturing cost drivers for "Should-Cost" models been provided? |  | 6 |  | C - Cost & Funding | C.2 - Cost Analysis
123 | Have the manufacturing costs been rolled up to the system/ commodity or sub-system level and been tracked against targets? |  | 7 |  | C - Cost & Funding | C.2 - Cost Analysis
124 | Are detailed trade studies and engineering change requests supported by cost estimates? |  | 7 |  | C - Cost & Funding | C.2 - Cost Analysis
125 | Are cost reduction and avoidance strategies underway? |  | 7 |  | C - Cost & Funding | C.2 - Cost Analysis
126 | Have the manufacturing cost drivers for "Should-Cost" models been updated? |  | 7 |  | C - Cost & Funding | C.2 - Cost Analysis
127 | Are costs analyzed using pilot line actuals to ensure target costs are achievable? |  | 8 |  | C - Cost & Funding | C.2 - Cost Analysis
128 | Does manufacturing cost analysis support proposed changes to requirements or configuration? |  | 8 |  | C - Cost & Funding | C.2 - Cost Analysis
129 | Are the cost reduction initiatives ongoing? |  | 8 |  | C - Cost & Funding | C.2 - Cost Analysis
130 | Have Low Rate Initial Production (LRIP) cost goals been met and has the learning curve been analyzed with actual data? |  | 9 |  | C - Cost & Funding | C.2 - Cost Analysis
131 | Are the cost reduction initiatives still ongoing? |  | 9 |  | C - Cost & Funding | C.2 - Cost Analysis
132 | Have the manufacturing cost drivers for "Should-Cost" models been updated? |  | 9 |  | C - Cost & Funding | C.2 - Cost Analysis
133 | Has touch labor efficiency been analyzed to meet production rates? |  | 9 |  | C - Cost & Funding | C.2 - Cost Analysis
134 | Have elements of inefficiency for touch labor been identified with plans in place for reduction? |  | 9 |  | C - Cost & Funding | C.2 - Cost Analysis
135 | Have Full Rate Production (FRP) cost goals been met? |  | 10 |  | C - Cost & Funding | C.2 - Cost Analysis
136 | Are the cost reduction initiatives continuing? |  | 10 |  | C - Cost & Funding | C.2 - Cost Analysis
137 | Have potential investments been identified? |  | 1 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
138 | Do the program/projects capabilities or commodities have reasonable budget estimates for reaching CMRL 3 through experiment? |  | 2 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
139 | Do the program/projects have reasonable budget estimates for reaching CMRL 4 by Milestone A? |  | 3 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
140 | Have manufacturing technology initiatives been identified to reduce costs? |  | 4 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
141 | Does the program have a reasonable budget estimate to reach CMRL 6 by Milestone B? |  | 4 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
142 | Does the cost estimate include capital investment for production-relevant equipment? |  | 4 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
143 | Are all outstanding CMRL 4 risk areas understood with approved mitigation plans in place? |  | 4 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
144 | Does the program have an updated budget estimate for reaching CMRL 6 by Milestone B? |  | 5 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
145 | Are all outstanding CMRL 5 risk areas understood with approved mitigation plans in place? |  | 5 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
146 | Does the program have a reasonable budget estimate for reaching CMRL 8 by Milestone C? |  | 6 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
147 | Does the cost estimate include capital investment for production-representative equipment by CDR the product development phase to demonstrate prior to the production phase? and pilot line equipment by Milestone C? |  | 6 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
148 | Are all outstanding CMRL 6 risk areas understood with approved mitigation plans in place? |  | 6 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
149 | Does the program have an updated budget estimate for reaching CMRL 8 by Milestone C? |  | 7 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
150 | Are all outstanding CMRL 7 risk areas understood with approved mitigation plans in place? |  | 7 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
151 | Does the program have a reasonable budget estimate for reaching CMRL 9 by the Full Rate Production (FRP) decision point? |  | 8 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
152 | Does the cost estimate include investment for Low Rate Initial Production (LRIP) and Full Rate Production (FRP)? |  | 8 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
153 | Are all outstanding CMRL 8 risk areas understood with approved mitigation plans in place? |  | 8 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
154 | Does the program have a reasonable budget estimate for Full Rate Production (FRP)? |  | 9 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
155 | Are all outstanding CMRL 9 risk areas understood with approved mitigation plans in place? |  | 9 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
156 | Are the production budgets sufficient for production at the required rates and schedule to support the funded program? |  | 10 |  | C - Cost & Funding | C.3 - Manufacturing Investment Budget
157 | Have material properties been identified for research? |  | 1 |  | D - Materials | D.1 - Maturity
158 | Have material properties and characteristics been predicted? |  | 2 |  | D - Materials | D.1 - Maturity
159 | Have material properties been validated and assessed for basic manufacturability using experiments? |  | 3 |  | D - Materials | D.1 - Maturity
160 | Have projected materials been produced in a laboratory environment? |  | 4 |  | D - Materials | D.1 - Maturity
161 | Have all materials been manufactured or produced in a prototype environment (may be in a similar application/program)? |  | 5 |  | D - Materials | D.1 - Maturity
162 | Are maturation efforts in place to address new material production risks for technology demonstration? |  | 5 |  | D - Materials | D.1 - Maturity
163 | Has the material maturity been verified with technology demonstration articles? |  | 6 |  | D - Materials | D.1 - Maturity
164 | Are preliminary material specifications in place? |  | 6 |  | D - Materials | D.1 - Maturity
165 | Have material properties been adequately characterized? |  | 6 |  | D - Materials | D.1 - Maturity
166 | Is the material maturity sufficient for a pilot line build? |  | 7 |  | D - Materials | D.1 - Maturity
167 | Have the necessary material specifications been approved? |  | 7 |  | D - Materials | D.1 - Maturity
168 | Have the materials been proven and validated during the Product Development Phase Engineering and Manufacturing Development (EMD) as adequate to support Low Rate Initial Production (LRIP)? |  | 8 |  | D - Materials | D.1 - Maturity
169 | Are material specifications stable? |  | 8 |  | D - Materials | D.1 - Maturity
170 | Have all necessary materials been proven and controlled to specification in Low Rate Initial Production (LRIP)? |  | 9 |  | D - Materials | D.1 - Maturity
171 | Are the materials proven and validated as adequate to support FRP? |  | 9 |  | D - Materials | D.1 - Maturity
172 | Have all necessary materials been proven and controlled to specification in Full Rate Production (FRP)? |  | 10 |  | D - Materials | D.1 - Maturity
173 | Has material availability been assessed? |  | 2 |  | D - Materials | D.2 - Availability
174 | Have material or capability scale-up issues been identified? |  | 3 |  | D - Materials | D.2 - Availability
175 | Have projected lead times been identified for all difficult to obtain, difficult to process, or hazardous materials? |  | 4 |  | D - Materials | D.2 - Availability
176 | Have material quantities and lead times been estimated? |  | 4 |  | D - Materials | D.2 - Availability
177 | Have material availability issues been addressed for the prototype and/or sample commodity build? |  | 5 |  | D - Materials | D.2 - Availability
178 | Have significant material risks been identified for all materials? |  | 5 |  | D - Materials | D.2 - Availability
179 | Has planning begun to address scale-up issues? |  | 5 |  | D - Materials | D.2 - Availability
180 | Have material availability issues been addressed to meet Engineering and Manufacturing Development (EMD) build? |  | 6 |  | D - Materials | D.2 - Availability
181 | Have Long-lead items been identified? |  | 6 |  | D - Materials | D.2 - Availability
182 | Have potential obsolescence issues been identified? |  | 6 |  | D - Materials | D.2 - Availability
183 | Have components capabilities or commodities been assessed for future DMSMS risk? |  | 6 |  | D - Materials | D.2 - Availability
184 | Have material availability issues been addressed to meet Engineering and Manufacturing Development (EMD) builds? |  | 7 |  | D - Materials | D.2 - Availability
185 | Have long lead procurements been identified/planned for Low Rate Initial Production (LRIP)? |  | 7 |  | D - Materials | D.2 - Availability
186 | Is an obsolescence plan in place? |  | 7 |  | D - Materials | D.2 - Availability
187 | Are mitigation strategies in place for DMSMS components commodities or materials? |  | 7 |  | D - Materials | D.2 - Availability
188 | Have long lead procurements been initiated for Low Rate Initial Production (LRIP)? |  | 8 |  | D - Materials | D.2 - Availability
189 | Are material availability risk issues minimized for Low Rate Initial Production (LRIP)? |  | 8 |  | D - Materials | D.2 - Availability
190 | Have long lead procurements been initiated for Full Rate Production (FRP)? |  | 9 |  | D - Materials | D.2 - Availability
191 | Are availability risk issues minimized for Full Rate Production (FRP)? |  | 9 |  | D - Materials | D.2 - Availability
192 | Are all significant Full Rate Production (FRP) material availability risk issues resolved? |  | 10 |  | D - Materials | D.2 - Availability
193 | Has an initial assessment of potential supply chain capability been completed? |  | 3 |  | D - Materials | D.3 - Supply Chain Management
194 | Has a survey for potential supply chain sources been completed? |  | 4 |  | D - Materials | D.3 - Supply Chain Management
195 | Have potential supply chain sources been identified and evaluated as able to support prototype build? |  | 5 |  | D - Materials | D.3 - Supply Chain Management
196 | Have life cycle supply chain requirements and the critical suppliers list been updated? |  | 6 |  | D - Materials | D.3 - Supply Chain Management
197 | Are supply chain plans (e.g., teaming agreements, etc.) in place leading to a Product Development Phase an Engineering and Manufacturing Development (EMD) contract award if applicable? |  | 6 |  | D - Materials | D.3 - Supply Chain Management
198 | Is there an effective supply chain management process defined, documented and in place? |  | 7 |  | D - Materials | D.3 - Supply Chain Management
199 | Has a plan been developed for establishing predictive indicators? |  | 7 |  | D - Materials | D.3 - Supply Chain Management
200 | Has an adequate assessment of the critical first tier supply chain been completed (i.e., capability, capacity, etc.)? |  | 7 |  | D - Materials | D.3 - Supply Chain Management
201 | Is the supply chain adequate to support Low Rate Initial Production (LRIP)? |  | 8 |  | D - Materials | D.3 - Supply Chain Management
202 | Has an adequate assessment of the critical second and lower tier supply chain been completed? |  | 8 |  | D - Materials | D.3 - Supply Chain Management
203 | Is there a robust and disciplined requirements flow-down process verified and in place? |  | 8 |  | D - Materials | D.3 - Supply Chain Management
204 | Has supplier compliance with program requirements and changes been validated? |  | 8 |  | D - Materials | D.3 - Supply Chain Management
205 | Has the plan for predictive indicators been updated for use in production? |  | 8 |  | D - Materials | D.3 - Supply Chain Management
206 | Is the supply chain stable and adequate to support Full Rate Production (FRP)? |  | 9 |  | D - Materials | D.3 - Supply Chain Management
207 | Are long term agreements in place where practical? |  | 9 |  | D - Materials | D.3 - Supply Chain Management
208 | Are the Prime's supplier management metrics (including thresholds and goals) in place and being used to manage risk? |  | 9 |  | D - Materials | D.3 - Supply Chain Management
209 | Are predictive indicators in place to manage suppliers? |  | 9 |  | D - Materials | D.3 - Supply Chain Management
210 | Has the supply chain been proven to support Full Rate Production (FRP) requirements? |  | 10 |  | D - Materials | D.3 - Supply Chain Management
211 | Has an initial evaluation of potential regulatory requirements and special handling concerns been completed? |  | 2 |  | D - Materials | D.4 - Special Handling
212 | Has a list of hazardous materials been identified? |  | 3 |  | D - Materials | D.4 - Special Handling
213 | Have potential special handling procedures been applied in the lab? |  | 3 |  | D - Materials | D.4 - Special Handling
214 | Have special handling concerns been assessed? |  | 3 |  | D - Materials | D.4 - Special Handling
215 | Has a list of hazardous materials been updated? |  | 4 |  | D - Materials | D.4 - Special Handling
216 | Have special handling requirements been identified? |  | 4 |  | D - Materials | D.4 - Special Handling
217 | Have the special handling procedures been applied in the lab? |  | 4 |  | D - Materials | D.4 - Special Handling
218 | Have special handling procedures been applied in a production relevant environment? |  | 5 |  | D - Materials | D.4 - Special Handling
219 | Have all special handling requirement gaps been identified? |  | 5 |  | D - Materials | D.4 - Special Handling
220 | Have new special handling processes been demonstrated in lab environment? |  | 5 |  | D - Materials | D.4 - Special Handling
221 | Have special handling procedures been applied in a production relevant environment? |  | 6 |  | D - Materials | D.4 - Special Handling
222 | Have the plans to address the special handling requirement gaps been completed? |  | 6 |  | D - Materials | D.4 - Special Handling
223 | Have special handling procedures been applied in a production representative environment? |  | 7 |  | D - Materials | D.4 - Special Handling
224 | Have special handling procedures been developed and annotated on work instructions for the pilot line? |  | 7 |  | D - Materials | D.4 - Special Handling
225 | Have special handling procedures been applied in a pilot line environment? |  | 8 |  | D - Materials | D.4 - Special Handling
226 | Have special handling procedures been demonstrated in the Product Development Phase Engineering and Manufacturing Development (EMD) or technology insertion programs? |  | 8 |  | D - Materials | D.4 - Special Handling
227 | Have the special handling risk issues been minimized for Low Rate Initial Production (LRIP)? |  | 8 |  | D - Materials | D.4 - Special Handling
228 | Do all work instructions contain special handling provisions as required? |  | 8 |  | D - Materials | D.4 - Special Handling
229 | Have special handling procedures been applied in a Low Rate Initial Production (LRIP) environment? |  | 9 |  | D - Materials | D.4 - Special Handling
230 | Have the special handling procedures been demonstrated in Low Rate Initial Production (LRIP)? |  | 9 |  | D - Materials | D.4 - Special Handling
231 | Have the special handling risk issues been minimized for Full Rate Production (FRP)? |  | 9 |  | D - Materials | D.4 - Special Handling
232 | Have the special handling procedures been effectively implemented in Full Rate Production (FRP)? |  | 10 |  | D - Materials | D.4 - Special Handling
233 | Have initial capability models been developed, if applicable? |  | 2 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
234 | Have proposed capability manufacturing concepts or producibility needs been identified based on high-level process flow chart models? |  | 3 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
235 | Have production modeling and simulation approaches for process or product capability or commodity been identified? |  | 4 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
236 | Have the initial simulation models (product or process capability or commodity) been developed at the component level and used to determine constraints? |  | 5 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
237 | Have the initial simulation models been developed at the technology sub-system or system level if applicable and used to determine system constraints? |  | 6 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
238 | Have the simulation models been used to determine system constraints and identify improvement opportunities? |  | 7 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
239 | Have the simulation models been verified by the pilot line? |  | 8 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
240 | Have the results of the simulation models been used to improve processes and determine that Low Rate Initial Production (LRIP) requirements can be met? |  | 8 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
241 | Have the simulation models been verified by Low Rate Initial Production (LRIP) build and used to assist in management of Low Rate Initial Production (LRIP)? |  | 9 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
242 | Have the results of the simulation models been used to determine if Full Rate Production (FRP) requirements can be met? |  | 9 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
243 | Have the simulation models been verified by Full Rate Production (FRP) build? |  | 10 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
244 | Have the production simulation models been used as a tool to assist in management of Full Rate Production (FRP)? |  | 10 |  | E - Process Capability & Control | E.1 - Modeling & Simulation
245 | Have material and/or process approaches been identified? |  | 2 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
246 | Have high level manufacturing processes been documented? |  | 3 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
247 | Have critical manufacturing processes for the capability or commodity been identified through experimentation? |  | 3 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
248 | Has a survey been completed to determine the current state of critical processes? |  | 4 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
249 | Has process maturity been assessed on similar capability or commodity processes in production? |  | 5 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
250 | Have process capability requirements been identified for pilot line, Low Rate Initial Production (LRIP) and Full Rate Production (FRP)? |  | 5 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
251 | Have the key manufacturing processes been demonstrated in a production relevant environment? |  | 6 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
252 | Has collecting or estimating process capability data from prototype build begun, and have process capability requirements been refined? |  | 6 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
253 | Have the manufacturing processes been successfully demonstrated in a production representative environment? |  | 7 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
254 | Has collecting or estimating process capability data continued? |  | 7 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
255 | Have process capability requirements been refined? |  | 7 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
256 | Have the manufacturing processes for Low Rate Initial Production (LRIP) been verified on a pilot line? |  | 8 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
257 | Does capability data from the pilot line meet the target? |  | 8 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
258 | Have process capability requirements for LRIP been refined based on Pilot Line data? |  | 8 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
259 | Are the manufacturing processes stable, adequately controlled, capable, and have the manufacturing processes achieved program Low Rate Initial Production (LRIP) objectives? |  | 9 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
260 | Have variability experiments been conducted to show Full Rate Production (FRP) impact and potential for continuous improvement? |  | 9 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
261 | Are the manufacturing processes stable, adequately controlled, capable, and have the manufacturing processes achieved program Full Rate Production (FRP) objectives? |  | 10 |  | E - Process Capability & Control | E.2 - Manufacturing Process Maturity
262 | Have initial estimates of yields and rates based on experiments or state of the art been completed? |  | 3 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
263 | Has a yield and rates assessment on proposed/similar processes been completed? |  | 4 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
264 | Has a yield and rates assessment on proposed/similar processes been applied within the Analysis of Alternatives (AoA) in the capabilities or commodities being selected? |  | 4 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
265 | Have target yield and rates been established for the pilot line, Low Rate Initial Production (LRIP), and Full Rate Production (FRP)? |  | 5 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
266 | Have yield and rate issues been identified and does the detailed production schedule support the required production rate? |  | 5 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
267 | Have yield and rate improvement plans been developed/initiated? |  | 5 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
268 | Are yields and rates from the production relevant environment being evaluated against targets? |  | 6 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
269 | Are results from the yields and rates from the production relevant environment being fed into an improvement plan? |  | 6 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
270 | Are yields and rates from the production representative environment being evaluated against pilot line targets? |  | 7 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
271 | Are results from the yields and rates from the production representative environment being fed into improvement plans? |  | 7 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
272 | Have pilot line yield and rate targets been achieved? |  | 8 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
273 | Have yields and rates required to begin Low Rate Initial Production (LRIP) been refined using pilot line articles? |  | 8 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
274 | Are yield and rate improvement plans ongoing and being updated? |  | 8 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
275 | Have the Low Rate Initial Production (LRIP) yield and rate targets been achieved? |  | 9 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
276 | Have the results of LRIP yields and rates been used to refine FRP yield requirements? |  | 9 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
277 | Are yield improvements on-going? |  | 9 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
278 | Have the Full Rate Production (FRP) yield and rate targets been achieved? |  | 10 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
279 | Are yield improvements on-going? |  | 10 |  | E - Process Capability & Control | E.3 - Process Yields and Rates
280 | Has a quality strategy been identified as part of the Technology Development Phase Technology Development Strategy (TDS) planning effort? |  | 4 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
281 | Is the updated quality strategy included in the System Engineering Plan (SEP)? |  | 4 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
282 | Has the quality strategy been updated to reflect Key Characteristic identification activities? |  | 5 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
283 | Is there an initial Quality Plan (QP) and a Quality Management System (QMS) in place? |  | 6 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
284 | Have quality risks and adequate metrics been identified and improvement plans initiated? |  | 6 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
285 | Have the quality targets been established? |  | 7 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
286 | Do Quality Management System (QMS) elements (e.g., control of nonconforming material, corrective action, etc.) meet requirements of appropriate industry standards? |  | 7 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
287 | Is a program capability or commodity-specific quality plan being developed? |  | 7 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
288 | Have the program capability or commodity-specific quality plan and Quality Manager been established? |  | 8 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
289 | Have quality targets been assessed against the pilot line? |  | 8 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
290 | Do quality target assessments drive continuous quality improvement? |  | 8 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
291 | Have quality targets been verified on the Low Rate Initial Production (LRIP) line? |  | 9 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
292 | Is continuous quality improvement on-going? |  | 9 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
293 | Is management review of quality targets conducted on a regular basis with appropriate action being taken? |  | 9 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
294 | Have the quality targets been verified on the Full Rate Production (FRP) line? |  | 10 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
295 | Is continuous quality improvement on-going? |  | 10 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
296 | Are statistical controls being applied where appropriate? |  | 10 |  | F - Quality Management | F.1 - Quality Management including Supplier Quality
297 | Has a product inspection and acceptance testing strategy been identified as part of the Technology Development Phase Planning efforts strategy? |  | 4 |  | F - Quality Management | F.2 - Product Quality
298 | Has a product inspection and acceptance testing strategy been included in the Systems Engineering Plan (SEP)? |  | 4 |  | F - Quality Management | F.2 - Product Quality
299 | Have roles and responsibilities been identified for acceptance test procedures, in-process and final inspections? |  | 5 |  | F - Quality Management | F.2 - Product Quality
300 | Have statistical process controls been identified for prototype commodity demonstration units? |  | 5 |  | F - Quality Management | F.2 - Product Quality
301 | Has a Key Characteristic management approach been defined? |  | 6 |  | F - Quality Management | F.2 - Product Quality
302 | Have initial requirements been identified for acceptance test procedures and in-process and final inspection requirements for EMD developmental units? |  | 6 |  | F - Quality Management | F.2 - Product Quality
303 | Have appropriate inspection and acceptance test procedures been identified for prototype capability or commodity demonstrations units? |  | 6 |  | F - Quality Management | F.2 - Product Quality
304 | Has quality data from the production representative environment been collected and analyzed and the results used to shape improvement plans? |  | 7 |  | F - Quality Management | F.2 - Product Quality
305 | Are control plans completed for management of Key Characteristics? |  | 7 |  | F - Quality Management | F.2 - Product Quality
306 | Are Test and Inspection Plans being developed for EMD development units? |  | 7 |  | F - Quality Management | F.2 - Product Quality
307 | Are Key Characteristics managed with measurement procedures and controls in place (e.g. SPC, FRACAS, audits, customer satisfaction, etc.)? |  | 8 |  | F - Quality Management | F.2 - Product Quality
308 | Does the Pilot line data meet capability requirements for all Key Characteristics? |  | 8 |  | F - Quality Management | F.2 - Product Quality
309 | Are Test and Inspection Plans complete and validated for production units? |  | 8 |  | F - Quality Management | F.2 - Product Quality
310 | Does data from LRIP demonstrate that production processes for all Key Characteristics and other manufacturing processes critical to quality are capable and under control for FRP? |  | 9 |  | F - Quality Management | F.2 - Product Quality
311 | Is the quality of Key Characteristics controlled at rate, and the data reflects only rare and unrepeated quality issues related to manufacturing processes? |  | 10 |  | F - Quality Management | F.2 - Product Quality
312 | Do results of quality data achieve targeted statistical level on all Key Characteristics? |  | 10 |  | F - Quality Management | F.2 - Product Quality
313 | Do results of quality data reflect continuous improvement? |  | 10 |  | F - Quality Management | F.2 - Product Quality
314 | Are potential supplier base quality capabilities and risks identified, to include subtier supplier quality management? |  | 4 |  | F - Quality Management | F.3 - Supplier Quality Management
315 | Have supply base quality capabilities and risks been identified, to include subtier quality management? |  | 5 |  | F - Quality Management | F.3 - Supplier Quality Management
316 | Have specific supply base quality improvement initiatives been identified addressing supplier Quality Management System shortfalls, including subtier supplier quality management? |  | 6 |  | F - Quality Management | F.3 - Supplier Quality Management
317 | Do key supplier Quality Management Systems meet appropriate industry standards? |  | 7 |  | F - Quality Management | F.3 - Supplier Quality Management
318 | Has supplier quality data from production representative units been collected and analyzed? |  | 7 |  | F - Quality Management | F.3 - Supplier Quality Management
319 | Has a strategy been outlined for audits of critical supplier processes? |  | 7 |  | F - Quality Management | F.3 - Supplier Quality Management
320 | Are supplier program-specific Quality Management Systems adequate ? |  | 8 |  | F - Quality Management | F.3 - Supplier Quality Management
321 | Have supplier products completed qualification testing? |  | 8 |  | F - Quality Management | F.3 - Supplier Quality Management
322 | Have supplier products completed first article inspection? |  | 8 |  | F - Quality Management | F.3 - Supplier Quality Management
323 | Is acceptance testing of supplier products adequate to begin LRIP? |  | 8 |  | F - Quality Management | F.3 - Supplier Quality Management
324 | Is a plan for subcontractor process audits in place and being implemented by prime contractor? |  | 8 |  | F - Quality Management | F.3 - Supplier Quality Management
325 | Does supplier management of quality of Key Characteristics and other critical manufacturing processes demonstrate capability and control for FRP? |  | 9 |  | F - Quality Management | F.3 - Supplier Quality Management
326 | Does acceptance testing of supplier products reflects control of quality adequate to begin FRP? |  | 9 |  | F - Quality Management | F.3 - Supplier Quality Management
327 | Are subcontractor Quality Audits performed as necessary to ensure subcontractor specification compliance? |  | 9 |  | F - Quality Management | F.3 - Supplier Quality Management
328 | Does supplier quality data reflect adequate management of Key Characteristics and control of critical manufacturing processes, including quality management down to subtier suppliers? |  | 10 |  | F - Quality Management | F.3 - Supplier Quality Management
329 | Does process quality achieve high statistical level (e.g. 6-sigma) on all critical dimensions? |  | 10 |  | F - Quality Management | F.3 - Supplier Quality Management
330 | Are subcontractor Quality Audits performed as necessary to ensure subcontractor specification compliance? |  | 10 |  | F - Quality Management | F.3 - Supplier Quality Management
331 | Have new manufacturing skills been identified? |  | 3 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
332 | Have manufacturing skill sets been identified? |  | 4 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
333 | Have production workforce requirements (technical and operational) been evaluated as part of AoA? |  | 4 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
334 | Has the availability of process development workforce for the Technology Development Phase been determined? |  | 4 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
335 | Have the necessary workforce skill sets been identified to meet prototype production capability or commodity demonstration manufacturing needs? |  | 5 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
336 | Have plans for the identified skill sets been developed to meet prototype production capability or commodity manufacturing needs? |  | 5 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
337 | Have special skills certification and training requirements been established? |  | 5 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
338 | Are the manufacturing workforce skills available for production in a relevant environment? |  | 6 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
339 | Have resources (quantities and skill sets) been identified to achieve requirements for pilot line and production? |  | 6 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
340 | Have initial plans for the identified resources (quantities and skill sets) been developed to achieve requirements for pilot line and production? |  | 6 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
341 | Have the manufacturing workforce resource requirements been identified for the pilot line? |  | 7 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
342 | Have plans been developed to achieve pilot line requirements? |  | 7 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
343 | Have plans been updated to achieve Low Rate Initial Production (LRIP) workforce requirements? |  | 7 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
344 | Has the pilot line workforce been trained in the representative environment? |  | 7 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
345 | Have manufacturing workforce resource requirements been identified for Low Rate Initial Production (LRIP)? |  | 8 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
346 | Have plans been developed to achieve Low Rate Initial Production (LRIP) requirements? |  | 8 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
347 | Have plans been updated to achieve Full Rate Production (FRP) workforce requirements? |  | 8 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
348 | Have Low Rate Initial Production (LRIP) personnel been trained on the pilot line where possible? |  | 8 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
349 | Have Low Rate Initial Production (LRIP) personnel requirements been met? |  | 9 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
350 | Has a plan been implemented to achieve Full Rate Production (FRP) workforce requirements? |  | 9 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
351 | Have Full Rate Production (FRP) personnel requirements been met including all necessary certifications? |  | 10 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
352 | Are production workforce skill sets being maintained due to attrition of the workforce? |  | 10 |  | G - Mfg Personnel | G.1 - Manufacturing Personnel
353 | Are tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements being considered as part of AoA? |  | 4 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
354 | Have tooling and STE/SIE requirements been identified? |  | 5 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
355 | Have supporting rationale and a schedule been provided for the tooling and STE/SIE requirements? |  | 5 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
356 | Have prototype tooling and STE/SIE concepts been demonstrated in production relevant environment? |  | 6 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
357 | Have production tooling and STE/SIE requirements been developed? |  | 6 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
358 | Are production tooling and STE/SIE design and development efforts underway? |  | 7 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
359 | Has a manufacturing equipment maintenance strategy been developed? |  | 7 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
360 | Have all tooling, test, and inspection equipment been proven on the pilot line? |  | 8 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
361 | Have all tooling, test and inspection equipment requirements been identified for Low Rate Initial Production (LRIP)? |  | 8 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
362 | Has manufacturing equipment maintenance been demonstrated on pilot line? |  | 8 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
363 | Have all tooling, test, and inspection equipment been proven in the Low Rate Initial Production (LRIP)? |  | 9 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
364 | Has all tooling, test, and inspection equipment been proven in LRIP and additional requirements identified for Full Rate Production (FRP)? |  | 9 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
365 | Has a manufacturing equipment maintenance schedule been demonstrated? |  | 9 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
366 | Is proven tooling, test, and inspection equipment in place to support maximum Full Rate Production (FRP)? |  | 10 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
367 | Has a planned equipment maintenance schedule been achieved? |  | 10 |  | H - Facilities | H.1 - Tooling/ Special Test and Inspection Equipment (STE/SIE)
368 | Have specialized facility requirements/needs been identified? |  | 3 |  | H - Facilities | H.2 - Facilities
369 | Has the availability of manufacturing facilities for prototype development and production been evaluated as part of the Analysis of Alternatives (AoA)? |  | 4 |  | H - Facilities | H.2 - Facilities
370 | Have manufacturing facilities been identified to produce prototypes demonstrate new capabilities or commodities? |  | 5 |  | H - Facilities | H.2 - Facilities
371 | Have plans for the identified manufacturing facilities been developed to produce prototypes demonstrate new capabilities or commodities? |  | 5 |  | H - Facilities | H.2 - Facilities
372 | Have manufacturing facilities been identified to produce the pilot line build? |  | 6 |  | H - Facilities | H.2 - Facilities
373 | Have plans for the identified manufacturing facilities been developed to produce the pilot line build? |  | 6 |  | H - Facilities | H.2 - Facilities
374 | Have manufacturing facilities been identified to produce the Low Rate Initial Production (LRIP) build? |  | 7 |  | H - Facilities | H.2 - Facilities
375 | Have plans for the identified manufacturing facilities been developed to produce the Low Rate Initial Production (LRIP) build? |  | 7 |  | H - Facilities | H.2 - Facilities
376 | Have pilot line facilities been demonstrated? |  | 8 |  | H - Facilities | H.2 - Facilities
377 | Are manufacturing facilities adequate to begin Low Rate Initial Production (LRIP)? |  | 8 |  | H - Facilities | H.2 - Facilities
378 | Are plans in place to support the transition to Full Rate Production (FRP)? |  | 8 |  | H - Facilities | H.2 - Facilities
379 | Is workplace safety adequate? |  | 8 |  | H - Facilities | H.2 - Facilities
380 | Have manufacturing facilities been demonstrated in Low Rate Initial Production (LRIP)? |  | 9 |  | H - Facilities | H.2 - Facilities
381 | Are capacity plans adequate to support Full Rate Production (FRP)? |  | 9 |  | H - Facilities | H.2 - Facilities
382 | Are the production facilities in place to meet Full Rate Production (FRP) requirements? |  | 10 |  | H - Facilities | H.2 - Facilities
383 | Has the capacity of the production facilities been demonstrated to meet Full Rate Production (FRP) requirements? |  | 10 |  | H - Facilities | H.2 - Facilities
384 | Has a manufacturing strategy been developed and integrated with an acquisition a capability or commodity development strategy? |  | 4 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
385 | Have prototype schedule risk mitigation efforts been incorporated into the Technology Development Phase efforts strategy (TDS)? |  | 4 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
386 | Has the manufacturing strategy been refined based upon the preferred concept? |  | 5 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
387 | Have prototype schedule risk mitigation efforts been initiated? |  | 5 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
388 | Has the initial manufacturing approach been developed? |  | 6 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
389 | Are all system design related manufacturing events included in the Integrated Master Plan/Schedule (IMP/S)? |  | 6 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
390 | Has the manufacturing risk mitigation approach for the pilot line or technology insertion programs been defined? |  | 6 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
391 | Has the initial manufacturing plan been developed if applicable? |  | 7 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
392 | Has manufacturing planning required to achieve CMRL 8 been included in the Integrated Master Plan/Schedule (IMP/S)? |  | 7 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
393 | Have manufacturing risks been integrated into risk mitigation plans? |  | 7 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
394 | Have initial work instructions been developed? |  | 7 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
395 | Is an effective production control system in place to support the pilot line? |  | 7 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
396 | Has the manufacturing plan been updated for Low Rate Initial Production (LRIP)? |  | 8 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
397 | Have all key manufacturing risks been identified and assessed with approved mitigation plans in place? |  | 8 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
398 | Have work instructions been finalized? |  | 8 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
399 | Is an effective production control system in place to support Low Rate Initial Production (LRIP)? |  | 8 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
400 | Has the manufacturing plan been updated for Full Rate Production (FRP)? |  | 9 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
401 | Have all manufacturing risks been tracked and mitigated? |  | 9 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
402 | Is an effective production control system in place to support Full Rate Production (FRP)? |  | 9 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
403 | Have all manufacturing risks been mitigated? |  | 10 |  | I - Mfg Management | I.1 - Mfg Planning & Scheduling
404 | Has the technology development article component list been developed with associated lead time estimates? |  | 4 |  | I - Mfg Management | I.2 - Materials Planning
405 | Is the technology development part list maturing? |  | 5 |  | I - Mfg Management | I.2 - Materials Planning
406 | Have make/buy evaluations begun? |  | 5 |  | I - Mfg Management | I.2 - Materials Planning
407 | Do the make/buy evaluations include production considerations reflecting the pilot line, Low Rate Initial Production (LRIP) and Full Rate Production (FRP) needs? |  | 5 |  | I - Mfg Management | I.2 - Materials Planning
408 | Are most material decisions complete (make/buy)? |  | 6 |  | I - Mfg Management | I.2 - Materials Planning
409 | Have material risks been identified? |  | 6 |  | I - Mfg Management | I.2 - Materials Planning
410 | Have material risk mitigation plans been developed? |  | 6 |  | I - Mfg Management | I.2 - Materials Planning
411 | Has the Bill of Materials (BOM) been initiated if applicable? |  | 6 |  | I - Mfg Management | I.2 - Materials Planning
412 | Are the make/Buy decisions and Bill of Materials (BOM) complete for pilot line build? |  | 7 |  | I - Mfg Management | I.2 - Materials Planning
413 | Are material planning systems in place for the pilot line build? |  | 7 |  | I - Mfg Management | I.2 - Materials Planning
414 | Are the Make/Buy decisions and Bill of Materials (BOM) complete to support Low Rate Initial Production (LRIP)? |  | 8 |  | I - Mfg Management | I.2 - Materials Planning
415 | Have material planning systems been proven on the pilot line and are in place for Low Rate Initial Production (LRIP) build? |  | 8 |  | I - Mfg Management | I.2 - Materials Planning
416 | Are the Make/Buy decisions and Bill of Materials (BOM) complete enough to support Full Rate Production (FRP)? |  | 9 |  | I - Mfg Management | I.2 - Materials Planning
417 | Has the material planning system been proven in LRIP, and is it sufficient for Full Rate Production (FRP? |  | 9 |  | I - Mfg Management | I.2 - Materials Planning
418 | Have the material planning systems been validated on the Full Rate Production (FRP) build? |  | 10 |  | I - Mfg Management | I.2 - Materials Planning