## Proposed
| Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4
A.1 Industrial Base | Existing | Throughout these criteria, because of the brevity, it was generally felt that there was not enough specificity in the statements (and terms needing defined). This could be accomplished in the MRL Users Guide, but has to be released at the same time as these new criteria. In keeping with instructions, no changes were made, just comments. |  | Potential sources identified to address technology needs. Understand state of the art. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes.
Understand the state of the art. Potential sources identified to address capability needs for concepts under consideration.
A.2 Manufacturing Technology Development | Existing |  | New manufacturing concepts and potential solutions identified. | Manufacturing technology concepts identified through experiments/models. | Manufacturing Science & Advanced Manufacturing Technology requirements identified.
| APT Proposed |  | Manufacturing Science (concepts, technologies, and capabilities) requirements identified to support potential solutions. | Advanced manufacturing technology concepts and capbilities identified. | Advanced Manufacturing Technology development requirements identified.
B.1 Producibility Program | Existing |  |  | Relevant materials/processes evaluated for manufacturability using experiments/models. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
|  |  | Identify potential characteristics of the concept (materials, processes, capabilities, limitations, etc.) that impact producibility. | Relevant materials and processes evaluated for producibility using experiments, models and simulations.
B.2 Design Maturity | Existing | Manufacturing research opportunities identified. | Applications defined. Broad performance goals identified that may drive manufacturing options. | Top level performance requirements defined. Trade-offs in design options assessed based on experiments. Product lifecycle and technical requirements evaluated. | SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred systems concepts.
| Notes: |  | Manufacturing and technical requirements identified that may drive manufacturing options. Broad performance goals identified. | Top level product performance, lifecycle, and technical requirements defined and evaluated. Trade-offs in design options assessed based on experiments. | Form, fit, and function constraints identified and manufacturing capabilities identified for preferred system concepts. SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified.
C.1 Production Cost Knowledge | Existing |  | Cost model approach defined. | Initial cost targets and risks identified. High level process chart model developed. Technology cost models developed for new process steps and materials based on experiments. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
| APT Proposed |  | Initial cost targets and risks identified. Cost model defined (initial process chart). | Initial cost models developed for process steps and materials (high-level process chart). Manufacturing cost estimates for potential solutions initiated. | Cost models include manufacturing, materials, and special requirements cost drivers. Cost models driven by process variables (detailed process chart). Cost driver uncertainties quantified.
C.2 Cost Analysis | Existing | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory). | Producibility cost risks assessed. Initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
| Notes: |  |  | Sensitivity analysis conducted to refine and quantify cost drivers, risks, and development strategy (e.g., lab to pilot line to factory). | Producibility and lifecycle cost risks assessed. Initial cost analysis supports Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
C.3 Manufacturing Investment Budget | Existing | Potential investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
| Jim's | Potential manufacturing investments identified. | Based on identified cost elements and risks, projects have reasonable manufacturing budget estimates to meet project goals. | Based on analysis, projects have reasonable manufacturing budget estimates for reaching MRL 4. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
D.1 Maturity | Existing | Material properties identified for research. | Material properties and characteristics predicted. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment.
| Jim's | Material characteristics and properties surveyed and identified for research. | Material properties defined based on research (literature, development, experiments, etc.).
D.2 Availability | Existing |  | Material availability assessed. | Material scale-up issues identified. | Projected lead times have been identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated.
| APT Proposed |  | Materials sources and availability identified. | Material availability and sourcing assessed. Material scale-up risks evaluated. Quantities and lead times estimated. | Projected lead times have been analyzed. Identify all difficult to obtain, difficult to process, or hazardous materials. Quantity and lead time risks determined.
D.3 Supply Chain Management | Existing |  |  | Initial assessment of potential supply chain capability. | Survey completed for potential supply chain sources.
| Jim's |  | Potential supply chain materials sources identified. | Initial assessment of potential supply chain, including capacity, capability, and sourcing conducted. | Supply chain capabilities analyzed with gaps and risks identified for preferred concept.
D.4 Special Handling | Existing |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Special handling procedures applied in the lab. Special handling concerns assessed. | List of hazardous materials updated. Special handling procedures applied in the lab. Special handling requirements identified.
| Jim's |  | Initial review and evaluation conducted of potential regulatory requirements and special handling concerns for applicability. | List of hazardous materials identified. Potential special handling concerns and regulatory requirements assessed. Special handling procedures applied. | List of hazardous materials updated. Special handling risks and issues identified. Special handling procedures are being followed.
E.1 Modeling & Simulation | Existing |  | Initial models developed, if applicable. | Identification of proposed manufacturing concepts or producibility needs based on high-level process flow chart models. | Production modeling/simulation approaches for process or product are identified.
| Jim's |  | Models and simulations developed to support analysis of the project/concept. | Modeling and simulations utilized to model behavior/performance of potential manufacturing solutions and define manufacturing concepts. | Modeling and simulations of manufacturing concepts are finalized.
E.2 Manufacturing Process Maturity | Existing |  | Identification of material and/or process approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Complete a survey to determine the current state of critical processes.
| Jim's |  |  | Feasibility assessments conducted identifying key/critical manufacturing processes and risks. | Complete an assessment to determine the current state of key/critical processes.
E.3 Process Yields and Rates | Existing |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA).
Jim's
F.1 Quality Management | Existing |  |  |  | Quality strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Jim's |  | Potential quality management risks identified. | Identify quality management strategy requirements that address initial needs and metrics. | Quality management strategy included in technology development and in systems engineering activities.
F.2 Product Quality | Existing |  |  |  | Product inspection and acceptance testing strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Jim's |  |  | Initial product quality requirements and risks identified. | Product inspection and acceptance testing strategy identified as part of the technology development and systems engineering activities.
F.3 Supplier Quality Management | Existing |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management.
| Jim's |  |  | Supplier Quality Management processes identified that address quality management needs and metrics.
G.1 Manufacturing Workforce | Existing |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
| Jim's |  |  | Identify workforce requirements, including new skills, unique, challenging, special skills, and training requirements.
H.1 Tooling / Special Test and Inspection Equipment (STE/SIE) | Existing |  |  |  | Tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements are considered as part of AoA.
| APT Proposed |  |  | Requirements for tooling and/or capital equipment for existing and new manufacturing processes identified. | Tooling, Special Test Equipment (STE), and Special Inspection Equipment (SIE) requirements including modifications, funding, and schedule are considered as part of AoA.
H.2 Facilities | Existing |  |  | Specialized facility requirements/needs identified. | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA.
| APT Proposed |  |  | Assess facilities under consideration for capabilities. | Capability and availability of manufacturing facilities for prototype development and production builds evaluated as part of trade studies or AoA.
I.1 Manufacturing Planning & Scheduling | Existing |  |  |  | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy.
| APT Proposed |  |  | Manufacturing concepts and systems to support trade studies identified and manufacturing strategy development (notional plans and schedules) initiated.
I.2 Materials Planning | Existing |  |  |  | Technology development article component list developed with associated lead time estimates.
| APT Proposed |  | Manufacturing considerations (planning and strategy ) for potential materials identified. | Specific considerations (availability, lead time, handling, storage, etc.) for the materials and components analyzed. | Materials and components list developed based on with estimates of availability, lead time, handling, storage, etc.
Note on E10: Author: Use of "technology" here is not clear needs definition.
Note on D25: Author: Questions about if we should keep "if applicable". Should we specify physics based models as an example or trade space models, or computational models.
Note on F25: Author: Models should be of three things: product, performance, or process
Note on F27: Author: Strong reactions about including definitions in the Users Guide.
Note on D31: Author: Comment was I can't manage quality in an area where there are no specs. No value for quality management here
Note on E35: Author: DoD doesn’t always allow resources to be available for this doing this at this time.
Note on E37: Author: is this the workforce in the lab or production define the skills to make the parts
Note on E39: Author: What kind of requirements? General requirements ROM System level requirements? High level requirements? NEED SPECIFICITY!
Note on F39: Author: Should this be stated as trade studies, or include trade studies? Definitions of what is meant by an AoA as a uniform definition should be in the deskbook and consistent throughout the thread.
Note on E41: Author: New capabilities specialized capabilities are we losing the focus on the potential risks production or prototype facilities? What type of facilities?