## Proposed
|  | MRL 1 | MRL 2 | MRL 3 | MRL 4
A.1 Industrial Base | Existing |  |  | Potential sources identified to address technology needs. Understand state of the art. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes.
| Proposed |  |  | Understand the state of the art. Potential sources identified to address capability needs for concepts under consideration. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes.
A.2 Manufacturing Technology Development | Existing |  | New manufacturing concepts and potential solutions identified. | Manufacturing technology concepts identified through experiments/models. | Manufacturing Science & Advanced Manufacturing Technology requirements identified.
| Proposed |  | Manufacturing Science (concepts and technologies) requirements identified to support potential solutions. | Advanced manufacturing technology concepts and capabilities identified. | Advanced manufacturing technology development requirements identified.
B.1 Producibility Program | Existing |  |  | Relevant materials/processes evaluated for manufacturability using experiments/models. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
| Proposed |  | Identify potential elements (materials, processes, capabilities, limitations) that impact producibility. | Relevant elements evaluated for producibility using experiments, models or simulations. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
B.2 Design Maturity | Existing | Manufacturing research opportunities identified. | Applications defined. Broad performance goals identified that may drive manufacturing options. | Top level performance requirements defined. Trade-offs in design options assessed based on experiments. Product lifecycle and technical requirements evaluated. | SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred systems concepts.
| Proposed | Manufacturing research opportunities identified. | Manufacturing and technical requirements identified that may drive manufacturing options. Broad performance goals identified. | Top level product performance, lifecycle, and technical requirements defined and evaluated. Trade-offs in design options assessed based on experiments or models. | SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred systems concepts.
C.1 Production Cost Knowledge | Existing |  | Cost model approach defined. | Initial cost targets and risks identified. High level process chart model developed. Technology cost models developed for new process steps and materials based on experiments. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
| Proposed |  | Cost model approach defined. | Initial cost models developed for process steps and materials (high-level process chart). Manufacturing cost estimates for potential solutions initiated. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
C.2 Cost Analysis | Existing | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory). | Producibility cost risks assessed. Initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
| Notes: | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to identify and quantify cost drivers, risks, and development strategy (e.g., lab to pilot line to factory). | Producibility and lifecycle cost risks assessed. Initial cost analysis supports Analysis of Alternatives (AoA) and Alternative Systems Review (ASR) or trade studies.
C.3 Manufacturing Investment Budget | Existing | Potential investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
| Proposed | Potential manufacturing investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
D.1 Maturity | Existing | Material properties identified for research. | Material properties and characteristics predicted. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment.
| Proposed | Material characteristics and properties surveyed and identified for research. | Material properties and characteristics predicted based on research. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment.
D.2 Availability | Existing |  | Material availability assessed. | Material scale-up issues identified. | Projected lead times have been identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated.
| Proposed |  | Materials sources and availability identified. | Material availability and sourcing assessed. Material scale-up risks identified and mitigation plans created. | Projected lead times have been identified. All difficult to obtain, difficult to process, or hazardous materials have been identified. Quantity and lead time estimated.
D.3 Supply Chain Management | Existing |  |  | Initial assessment of potential supply chain capability. | Survey completed for potential supply chain sources.
| Proposed |  |  | Initial assessment of potential supply chain capability. | Supply chain capabilities analyzed with gaps and risks identified for preferred concept.
D.4 Special Handling | Existing |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Special handling procedures applied in the lab. Special handling concerns assessed. | List of hazardous materials updated. Special handling procedures applied in the lab. Special handling requirements identified.
| Proposed |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Potential special handling concerns defined and regulatory requirements assessed. Special handling procedures assessed. | List of hazardous materials updated. Special handling risks and issues identified. Special handling procedures are being followed.
E.1 Modeling & Simulation | Existing |  | Initial models developed, if applicable. | Identification of proposed manufacturing concepts or producibility needs based on high-level process flow chart models. | Production modeling/simulation approaches for process or product are identified.
| Proposed |  | Initial models developed, if applicable. | Production modeling/simulation approaches for process or product are identified. | Modeling and simulations utilized to model behavior/performance of potential manufacturing solutions and defined manufacturing concepts. Key predictive process variables extracted from manufacturing trials or DOEs.
E.2 Manufacturing Process Maturity | Existing |  | Identification of material and/or process approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Complete a survey to determine the current state of critical processes.
| Proposed |  | Identification of potential processing approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Current state of key/critical processes assessed against program requirements.
E.3 Process Yields and Rates | Existing |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA).
| Proposed |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA).
F.1 Quality Management | Existing |  |  |  | Quality strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Proposed |  |  |  | Quality management strategy included in technology development and in systems engineering activities.
F.2 Product Quality | Existing |  |  |  | Product inspection and acceptance testing strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Proposed |  |  | Initial product quality requirements and risks identified. Inspection technologies identified. | Product inspection and acceptance testing strategy identified as part of the technology development and systems engineering activities.
F.3 Supplier Quality Management | Existing |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management.
| Proposed |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management.
G.1 Manufacturing Workforce | Existing |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
| Proposed |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
H.1 Tooling / Special Test and Inspection Equipment (STE/SIE) | Existing |  |  |  | Tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements are considered as part of AoA.
| Proposed |  |  |  | Tooling, Special Test Equipment (STE), Special Inspection Equipment (SIE) requirements, including modifications, funding, and schedule, are considered as part of AoA or trade studies.
H.2 Facilities | Existing |  |  | Specialized facility requirements/needs identified. | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA.
| Proposed |  |  | Specialized facility requirements/needs identified. | Capability and availability of manufacturing facilities for prototype development and production evaluated as part of AoA or trade studies.
I.1 Manufacturing Planning & Scheduling | Existing |  |  |  | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy.
| Proposed |  |  | Manufacturing concepts to support trade studies identified. Manufacturing strategy development (notional plans and schedules) initiated. | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy.
I.2 Materials Planning | Existing |  |  |  | Technology development article component list developed with associated lead time estimates.
| Proposed |  | Initial plans and strategies for potential materials identified. | Specific considerations (availability, lead time, handling, storage) for materials and components idenitified. | Materials and components list developed with estimates of availability, lead time, handling, storage, etc.