## Version_2020
Version 2018 | DoD Manufacturing Readiness Levels (MRLs)
Acquisition Phase |  | Pre-Materiel Development Decision (Pre-MDD) |  |  | Materiel Solution Analysis (MSA) | Technology Maturation and Risk Reduction (TMRR) |  | Engineering & Manufacturing Development (EMD) |  | Low-Rate Initial Production (LRIP) | Full-Rate Production (FRP)
Technical Reviews |  |  |  |  | ASR | SRR/SFR | PDR | CDR | PRR/SVR | PCA
Thread | Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4 | MRL 5 | MRL 6 | MRL 7 | MRL 8 | MRL 9 | MRL 10 | NOTES
| Technology Maturity | Should be assessed at TRL 1. | Should be assessed at TRL 2. | Should be assessed at TRL 3. | Should be assessed at TRL 4. | Should be assessed at TRL 5. | Should be assessed at TRL 6. | Should be assessed at TRL 7 | Should be assessed at TRL 7 or TRL 8. | Should be assessed at TRL 8 or TRL 9. | Should be assessed at TRL 9.
A - Technology and Industrial Base | A.1 Industrial Base | Global trends in emerging industrial base capabilities identified. | Potential industrial base capability gaps identified. | Industrial base capabilities for potential sources identified for system concepts. OT Cybersecurity threats and risks in the anticipated industrial base have been identified. Potential manufacturing and quality systems OT cybersecurity capabilities and gaps identified. | Industrial base capabilities surveyed for preferred materiel solution, key technologies, components, and/or key processes. Industrial base capability risks and issues included in AoA. OT Cybersecurity threats and risks in the anticipated industrial base have been identified and risk management plans developed. Industrial Base OT cyber vulnerability and cybersecurity capabilities identified. | Industrial base capabilities assessment (including OT cybersecurity) initiated to identify potential manufacturing sources. Sole/single/foreign source vendors and vendors of technologies with potential obsolescence issues, and/or cyber vulnerabilities identified, and planning initiated to minimize risks. Industrial base OT cybersecurity vulnerabilities identified. | Industrial base capabilities assessment for MS B completed. Industrial capability in place to support manufacturing of development articles. Plans to minimize sole/single/foreign sources, and obsolescence issues, and OT cyber vulnerabilities complete. Need for sole/single/foreign sources justified. Potential alternative sources identified. | Industrial capability to support production analyzed. Sole/single/foreign sources, source stability, and obsolescence, and OT cyber vulnerability issues are assessed/ monitored. Potential alternate sources developed if necessary. | Industrial base capability assessment for MS C completed. Secure and trusted [Need to discuss what this means] Industrial capability is in place to support LRIP. Sources are available, including multi-sourcing where cost-effective or necessary to mitigate risk. | Secure and trusted [Need to discuss what this means] Industrial capability assessment for FRP has been completed and capability is in place to support start of FRP. | Secure and trusted [Need to discuss what this means] Industrial capability supports FRP and is assessed to support modifications, upgrades, surge and other potential manufacturing requirements. | 1. Added "OT" throughout 2. MRL 5 - made last part a separate sentence 3. Need to discuss meaning of "secure and trusted" - this can mean something very specific, which would not apply to all suppliers 4. Added OT to the Acronym tab and deleted words.
| A.2 Manufacturing Technology Development | Global trends in manufacturing science and technology identified (i.e., concepts, capabilities). | Potential manufacturing science and technology gaps identified. | Manufacturing technology requirements identified to address potential capability gaps for system concepts. | Manufacturing technology development initiatives defined for preferred materiel solution. Manufacturing technology development requirements considered in the AoA. | Required manufacturing technology development efforts initiated. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions (including OT cyber security) demonstrated in a production relevant environment. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions (including OT cyber security) demonstrated in a production representative environment. | Primary manufacturing technology efforts concluding. Improvement efforts continuing. Required manufacturing technology solutions (including OT cyber security) validated on a pilot line. | Manufacturing technology process improvements (including OT cyber security) efforts initiated for FRP. | Manufacturing technology (including OT cyber security) continuous process improvements ongoing. | Added "OT" throughout; otherwise team agreed this was OK
B - Design | B.1 Producibility Program | Hypotheses developed for cause-effect relationships between technology variables and producibility. | Studies performed to test hypotheses regarding cause-effect relationships between technology variables and producibiity. Elements identified which have a potential impact producibility (i.e., materials, processes, capabilities, limitations). | System concept elements evaluated for manufacturability and producibility using experiments, modeling, and simulation. | Initial producibility and manufacturability assessments in selection of preferred materiel solution completed. Results considered in AoA and documented in AS key components/ technologies. | Producibility and manufacturability assessments of key technologies and components initiated. Ongoing design trades consider manufacturing processes and industrial base capability constraints. Manufacturing processes assessed for capability to be tested and verified in production. Manufacturing processes assessed for influence on O&S. | Producibility assessments and producibility trade studies (performance vs. producibility) of key technologies/components completed. Results used to shape AS, SEP, manufacturing and producibility plans, and planning for EMD or technology insertion programs. Preliminary design choices assessed against manufacturing processes and industrial base capability constraints. Producibility enhancement efforts (i.e., DFM, DFA, etc.) initiated. | Detailed producibility trade studies using knowledge of key design characteristics and related manufacturing process capability completed. Producibility enhancement efforts (i.e., DFM, DFA, etc.) ongoing for optimized integrated system. Manufacturing processes re-assessed as needed for capability to be tested and verified. Manufacturing processes re-assessed as needed for potential influence on O&S. | Producibility improvements implemented on system. Known producibility risks and issues managed for LRIP. | Prior producibility improvements analyzed for effectiveness during LRIP. Producibility risks and issues discovered in LRIP managed for FRP. | Design producibility improvements demonstrated in FRP. Process producibility improvements ongoing. All modifications, upgrades, DMSMS and other changes assessed for producibility. | No new criteria
| B.2 Design Maturity | Current capability deficiencies and gaps identified. | Analyses performed to evaluate the feasibility of potential solutions to address capability gaps. | High level performance, lifecycle, and technical requirements defined and evaluated for system concepts. Trade-offs in design options based on experiments and initial MOEs. | Form, fit, and function constraints, and manufacturing capabilities identified for preferred systems concept. SEP and T&E Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial KPPs identified for preferred systems concept. System characteristics and measures to support required capabilities identified. | Lower level performance requirements sufficient to proceed to preliminary design. All enabling/critical technologies and components identified and the product lifecycle considered. Evaluation of the design for KCs initiated. Product data required for prototype component manufacturing released. | System allocated baseline established. Product requirements and features are well enough defined to support PDR. Product data essential for subsystem/ system prototyping has been released, and all enabling/critical components have been prototyped. Preliminary KCs for the design identified and mitigation plans initiated. | Product design and features are well enough defined to support CDR, even though design change traffic may be significant. All product data essential for component manufacturing released. Potential KC risks and issues identified with mitigation plans in place. | Detailed design of product features and interfaces completed. All product data essential for system manufacturing released. Design change traffic does not significantly impact LRIP. KCs are attainable based upon pilot line demonstrations. | Major product design features and configuration are stable. System design has been validated through operational testing of LRIP items. PCA or equivalent complete as necessary. Design change traffic is limited. All KCs are controlled in LRIP to appropriate quality levels. | Product design is stable. Design changes are few and generally limited to those required for continuous improvement or in reaction to obsolescence. All KCs are controlled in FRP to appropriate quality levels. | No new criteria
C - Cost & Funding | C.1 Production Cost Knowledge (Cost modeling) | Hypotheses developed regarding technology impact on affordability. | Cost model approach defined. | Manufacturing cost estimates for system concepts developed. Initial cost models developed which include high-level process steps and materials. | Cost estimates refined based on anticipated production volumes associated with preferred materiel solution. Cost model updated with identified cost drivers (i.e., process variables, manufacturing, materials, and special requirements).Cost driver uncertainty quantified. Cost model supports AoA and ASR. | Prototype components produced in a production relevant environment, or simulations drive end-to-end cost models. Cost model includes materials, labor, equipment, tooling/STE/SIE, setup, yield/scrap/rework, WIP, and capability/capacity constraints. | Cost model updated with design requirements, material specifications, tolerances, IMS, results of system/subsystem simulations and production relevant prototype demonstrations. | Cost model updated with the results of systems/sub-systems produced in a production representative environment, production plant layout and design, and obsolescence solutions. | Cost model updated with results of pilot line build. | FRP cost model updated with result of LRIP build. | Cost model validated against actual FRP cost. | No new criteria
| C.2 Cost Analysis | Initial manufacturing and quality costs identified. | Potential manufacturing and quality cost drivers and system affordability gaps identified. | Analyses conducted to refine manufacturing and quality cost drivers, risks, and development strategy (e.g., lab to pilot to factory). Potential cost reduction and system affordability gap closure strategies identified. | Producibility and lifecycle cost risks and issues assessed for preferred materiel solution. Initial cost analysis supports AoA and ASR. | Costs analyzed using prototype component actuals to ensure target costs are achievable. Decisions regarding design choices, make/buy, capacity, process capability, sources, quality, KCs, yield/rate, and variability influenced by cost models. | Costs analyzed using prototype system/sub-system actuals to ensure target costs are achievable. Cost targets allocated to subsystems. Cost reduction and avoidance strategies developed. Manufacturing cost drivers for "Should-Cost" model provided. | Manufacturing costs rolled up to system/sub-system level and tracked against targets. Detailed trade studies and engineering change requests supported by cost estimates. Cost reduction and avoidance strategies underway. Manufacturing cost drivers for "Should-Cost" model updated. | Costs analyzed using pilot line actuals to ensure target costs are achievable. Manufacturing cost analysis supports proposed changes to requirements or configuration. Cost reduction initiatives ongoing. Manufacturing cost drivers for "Should-Cost" model updated. | LRIP cost goals met and learning curves analyzed with actual data. Cost reduction initiatives ongoing. Touch labor efficiency analyzed to meet production rates and elements of inefficiency are identified with plans in place for reduction. | FRP cost goals met. Cost reduction initiatives ongoing. | No new criteria
| C.3 Manufacturing Investment Budget | Potential manufacturing investment strategy developed. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. Manufacturing investment budget ROM estimates identified to support industrial base and manufacturing capability gap closure strategies. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. Preliminary manufacturing investment budget estimates for manufacturing gap closure recommendations have been developed. | Manufacturing technology budget initiatives developed and incorporated to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production relevant equipment. All outstanding MRL 4 risks and issues understood with approved mitigation plans in place. | Program has updated budget estimate for reaching MRL 6 by MS B. All outstanding MRL 5 risks and issues understood with approved mitigation plans in place. | Program has reasonable budget estimate for reaching MRL 8 by MS C. Estimate includes capital investment for production-representative equipment by CDR and pilot line equipment by MS C. All outstanding MRL 6 risks and issues understood with approved mitigation plans in place. | Program has updated budget estimate for reaching MRL 8 by MS C. All outstanding MRL 7 risks and issues understood with approved mitigation plans in place. | Program has reasonable budget estimate for reaching MRL 9 by the FRP decision point. Estimate includes investment for LRIP and FRP. All outstanding MRL 8 risks and issues understood with approved mitigation plans in place. | Program has reasonable budget estimate for FRP. All outstanding MRL 9 risks and issues understood with approved mitigation plans in place. | Production budgets sufficient for production at required rates and schedule to support funded program. | No new criteria
D - Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | D.1 Maturity | New material properties and characteristics surveyed and identified for research (e.g., manufacturability, quality). | Potential effects of new material properties on design application manufacturability and quality predicted based on research. | Effects of new material properties on design concept manufacturability and quality validated using experiments and models. | New materials and components for preferred materiel solution demonstrated in a laboratory environment. | Materials manufactured or produced in a prototype environment (may be in a similar application/program). Maturation efforts in place to address new material production risks for technology demonstration. | Material maturity verified through technology demonstration articles. Preliminary material specifications in place. Material properties adequately characterized. | Material maturity sufficient for pilot line build. Material specifications approved. | Materials proven and validated during EMD as adequate to support LRIP. Material specifications stable. | Materials controlled to specifications in LRIP. Materials proven and validated as adequate to support FRP. | Materials controlled to specifications in FRP. | No new criteria
| D.2 Availability | Global trends for material availability, obsolescence, and DMSMS surveyed and identified for research. | Material availability, obsolescence, and DMSMS gaps identified. | Material availability, obsolescence, and DMSMS gap closure strategy defined. | Projected lead times identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated. Material availability risks and issues for preferred materiel solution considered in AoA. Mitigation plans incorporated in SEP for the preferred system concept. | Availability risks and issues addressed for prototype build. Significant material risks identified for all materials. Planning initiated to address scale-up issues. | Availability risks and issues addressed to meet EMD build. Long-lead items identified. Potential obsolescence issues identified. Components assessed for future DMSMS risk. | Availability risks and issues addressed to meet LRIP builds. Long lead procurements identified and mitigated. Obsolescence plan in place. DMSMS mitigation strategies for components in place. | Availability risks and issues managed for LRIP. Long lead procurement initiated for LRIP. Availability issues addressed to meet FRP builds. | Long lead procurement initiated for FRP. Availability risks and issues managed for FRP. | All material availability risks and issues managed. | No new criteria
| D.3 Supply Chain Management | Global trends for supply chain capability and capacity surveyed. | Potential supply chain capability and capacity gaps identified. | Supply chain capability and capacity gap closure strategies defined. Potential OT cybersecurity capabilities and cyber-vulnerabilities identified. | Survey of potential supply chain sources for preferred materiel solution completed. Supply chain capability and capacity analyses considered in the AoA. OT Cybersecurity capabilities and cyber-vulnerabilities evaluated. | Potential supply chain sources identified and evaluated as able to support prototype build. Supply chain OT cyber security and vulnerability risks and issues assessed with mitigation/incident plans initiated. [Is this a new plan we need to define? Or is it an MMP?] | Lifecycle Supply Chain requirements updated. Critical suppliers list updated. Supply chain plans in place (e.g. teaming agreements, etc.) supporting an EMD contract award. Supply chain OT cyber security and vulnerability risk mitigation plans developed. [Is this a new plan? Or MMP?] Cyber incident handling system developed. | Effective supply chain management processes defined, documented, and in place. Plan developed for predictive indicators. Assessment of critical first tier supply chain completed (i.e., capability, capacity, etc.). Supply chain OT cyber security and vulnerability risk mitigation plans implemented. [Are these new plans or MMPs?] Cyber incident management system including reporting, tracking, and corrective actions, in place. | Assessment of critical second and lower tier supply chain completed. Robust requirements flow down processes in place and verified. Supplier compliance with program requirements and changes validated. Plan for predictive indicators for use in production updated. Supply chain adequate to support LRIP. Supply Chain Cyber OT incident management system indicates low acceptable risk for initial production. | Long term agreements in place where practical. Prime's supplier management metrics (including thresholds and goals) in place and used to manage risks. Predictive indicators to manage suppliers in place. Supply chain is stable and adequate to support FRP. Supply Chain OT Cyber incident management system indicates no known risks and low acceptable risk for rate production. | Supply chain proven and supports FRP requirements. Minimal OT cyber security incident occurance. Prompt incident identification and corrective actions minimizing impacts. OT Cyber incidents are identified and corrected prior to impacting production. | 1. Added "OT" throughout 2. Need to discuss: Are thses risk mitigation plans the same as MMPs? Or something different that we need to define? 3. Changed "low risk" to "acceptable risk" 4. Reworded MRL 10 to avoid unclear timing of "prompt"
| D.4 Special Handling (i.e. GFP, shelf life, security, hazardous materials, storage environment, ESH, etc.) | Hazardous materials identified and safety procedures in place. | Initial evaluation of potential regulatory requirements and special handling concerns. Raw materials and components assessed for special handling and potential regulatory requirements. | ESH compliance risk identified. List of hazardous materials identified and alternatives evaluated. Special handling procedures applied in the lab. Special handling concerns assessed. | ESH compliance risk mitigated in lab environment. List of hazardous materials updated and alternatives assessed. Special handling procedures applied and disposal procedures evaluated. Special handling requirements identified, and analyzed, and documented in the SEP. | ESH requirements and special handling procedures applied in production relevant environment. Special handling (including security, physical and cyber) requirement gaps identified. New special handling processes demonstrated in lab environment. | ESH requirements addressed and documented. Special handling procedures (including security, physical and cyber) demonstrated in production relevant environment. Plans to address special handling requirement gaps, risks, and issues complete. Manufacturing assessed for material storage and waste handling risks. | ESH compliance demonstrated in production representative environment. Special handling procedures (including security, physical and cyber) applied in production representative environment. Special handling procedures developed and annotated on work instructions for pilot line. Hazardous material storage and disposal plan in place for the pilot line. | ESH compliance demonstrated in pilot line production. Special handling procedures (including security, physical and cyber) applied in pilot line environment and demonstrated in EMD or technology insertion programs. Special handling risks and issues managed for LRIP. All work instructions contain special handling provisions as required. Hazardous material storage and disposal plan evaluated and in place for LRIP. | ESH compliance demonstrated in LRIP. Special handling (including security, physical and cyber), and hazardous material storage and disposal procedures demonstrated in LRIP environment. Special handling, and hazardous material storage and disposal risks and issues managed for FRP. | ESH compliance demonstrated in FRP. Special handling (including security, physical and cyber) and hazardous material storage and disposal procedures effectively implemented in FRP. | Security is already included under Special Handling. This includes both physical and cyber.
E - Process Capability & Control | E.1 Modeling & Simulation (Product & Process) | Modeling and simulation approaches/tools identified to support manufacturing and quality activities. | Initial modeling and simulation development initiated. | Manufacturing and quality gaps for system concepts identified using modeling and simulation. | Production modeling and simulation tools utilized to define manufacturing and quality requirements for preferred materiel solution. Modeling and simulation results considered in the AoA. | Initial modeling & simulations (product or process) developed at the component level and used to determine constraints. | Initial modeling & simulations developed at the sub-system or system level, and used to determine system constraints. | Modeling & simulations used to determine system constraints and to identify improvement opportunities. | Modeling & simulations verified by pilot line build. Results used to improve process and demonstrate that LRIP requirements can be met. | Modeling & simulations verified by LRIP build, assist in management of LRIP, and demonstrate that FRP requirements can be met. | Modeling & simulations verified by FRP build. Production simulation models used as tools to assist in management of FRP.
| E.2 Manufacturing Process Maturity | Hypotheses developed regarding cause-effect relationships between process variables and process stability and repeatability. | Studies performed to test hypotheses regarding cause-effect relationships. Initial process approaches identified. | Cause-effect relationships between process control variables and process stability and repeatability validated through laboratory experiments. Critical process control variables identified. | Maturity of critical processes for preferred materiel solution assessed. Process capability requirements and improvement plans developed and documented in the SEP. | Process Maturity assessed on similar processes in production. Process capability requirements identified for pilot line, LRIP and FRP. | Manufacturing processes demonstrated in production relevant environment. Collection or estimation of process capability data from prototype build and refinement of process capability requirements initiated. | Manufacturing processes demonstrated in a production representative environment. Collection and/or estimation of process capability data and refinement of process capability requirements ongoing. | Manufacturing processes for LRIP verified on a pilot line. Process Capability data from pilot line meets target. Process capability requirements for LRIP and FRP refined based upon pilot line data. | Manufacturing processes are stable, adequately controlled, capable, and have achieved program LRIP objectives. Variability experiments conducted to show FRP impact and potential for continuous improvement. | Manufacturing processes are stable, adequately controlled, capable, and have achieved program FRP objectives. | Should this Sub-Thread include interoperability?
| E.3 Process Yields and Rates | Hypotheses developed regarding future state manufacturing yields and rates. | Studies performed to test hypotheses regarding yields and rates. | Initial estimates of yields and rates for system concepts identified through laboratory experiments. Yield and rate gaps for system concepts identified. | Yield and rate assessments on preferred materiel solution completed and considered in the AoA. Yield and rate gap closure strategies identified for the preferred materiel solution and documented in the SEP. | Target yields and rates established for pilot line, LRIP, and FRP. Yield and rate issues identified. Improvement plans developed/initiated. | Yields and rates from production relevant environment evaluated against targets and the results feed improvement plan. | Yields and rates from production representative environment evaluated against pilot line targets and the results feed improvement plans. | Pilot line targets achieved. Yields and rates required to begin LRIP refined using pilot line results. Improvement plans ongoing and updated. | LRIP yield and rate targets achieved. Yields and rates required to begin FRP refined using LRIP results. Yield improvements on-going. | FRP yield and rate targets achieved. Yield improvements on-going.
F - Quality | F.1 Quality Management | Quality management considerations surveyed and included in early planning activities | Quality management needs assessed, analyzed, and validated. | Quality management requirements for system concepts identified | Quality strategy for the preferred materiel solution developed, considered in the AoA, and documented in the SEP and the AS. | Quality strategy updated to reflect KC identification activities. | Initial Quality Plan and QMS are in place. Quality risks, issues, and metrics have been identified and improvement plans initiated. | Quality targets established. QMS elements (i.e., control of nonconforming material, corrective action, etc.) meet requirements of appropriate industry standards. Program-specific Quality Program Plan developed. | Program-specific Quality Program Plan established. Program Quality Manager assigned. Quality targets assessed against pilot line, results feed continuous quality improvements. | Quality targets verified on LRIP line. Continuous quality improvement on-going. Management review of Quality measures conducted on regular basis and appropriate actions taken. | Quality targets verified on FRP line. Continuous quality improvement on-going. Statistical controls applied where appropriate.
| F.2 Product Quality | Quality metrology state of the art surveyed. Hypotheses developed regarding cause-effect relationships between technology variables and quality. | Studies performed to test hypotheses regarding cause-effect relationships between technology variables and quality. Elements identified which have a potential impact on quality (i.e., materials, processes, capabilities, limitations). | System concept elements evaluated for quality using experiments, modeling and simulation. Initial product quality requirements, risks, and issues identified. Inspection technologies identified. | Product quality requirements and the inspection and acceptance testing strategy for the preferred materiel solution considered in AoA and documented in the AS. Product quality risk and issue mitigation plans documented in the SEP. | Roles and responsibilities identified for acceptance test procedures, in-process and final inspections, and statistical process controls for prototype units. | KC management approach defined. Initial requirements identified for acceptance test procedures and in-process and final inspection requirements for EMD units. Appropriate inspection and acceptance test procedures identified for prototype units. | Quality data from the production representative environment collected and analyzed and results used to shape improvement plans. Control plans completed for management of KCs. Test and Inspection plans being developed for EMD units. | KCs managed. Measurement procedures and controls in place (e.g. SPC, FRACAS, audits, customer satisfaction, etc.). Pilot line data meets capability requirements for all KCs. Test and Inspection plans complete and validated for production units. | Data from LRIP demonstrates production processes, for all KCs and other manufacturing processes critical to quality, are capable and under control for FRP. | KCs controlled at rate. Results achieve targeted statistical level on all KCs. Results reflect continuous improvement.
| F.3 Supplier Quality/ Management | Supplier quality and quality management systems state of the art surveyed. | Initial supplier quality and quality management systems evaluated. | Supplier quality and quality management system requirements for system concepts identified. | Potential supplier quality capabilities, risks, and issues identified for the preferred materiel solution, including subtier suppliers. Supplier quality management system requirements defined, and documented in the AS. | Supply base quality capabilities and risks identified, including subtier supplier quality management. | Supply base quality improvement initiatives identified addressing supplier QMS shortfalls, including subtier supplier quality management. | Key supplier QMSs meet appropriate industry standards. Supplier quality data from production representative units collected and analyzed. Strategy for audits of critical supplier processes outlined. | Supplier program-specific QMSs adequate. Supplier products qualification testing and first article inspection completed. Acceptance testing of supplier products adequate to begin LRIP. Plan for subcontractor process audits in place and implemented by prime contractor. | Supplier quality management of KCs and other critical manufacturing processes demonstrates capability and control for FRP. Acceptance testing of supplier products reflects control of quality adequate to begin FRP. Subcontractor quality audits performed as necessary to ensure subcontractor specification compliance. | Supplier quality data reflects adequate management of KCs and control of critical manufacturing processes, including quality management down to subtier suppliers. Results achieve high statistical level (e.g., 6-sigma) on all critical dimensions. Subcontractor quality audits performed as necessary to ensure subcontractor specification compliance.
G - Manufacturing Workforce (Engineering & Production) | G.1 Manufacturing Workforce (Engineering & Production) | Workforce skill sets to support emerging trends in manufacturing and technology surveyed. | Workforce skill sets to support emerging trends in manufacturing and technology evaluated. | Workforce skill set requirements for system concepts identified. Workforce skill set capability gaps identified | Workforce skill sets and production workforce requirements (technical and operational) for the preferred materiel solution identified and considered in the AoA. Workforce training and development requirements defined to close skill set gaps defined. Availability of workforce for TMRR Phase determined. | Skill sets identified and plans developed to meet prototype and production needs. Special skills certification and training requirements established. Special skills, certifications, cyber security, etc. training requirements established. Screened workforce trained in cyber security. | Manufacturing workforce skills available for the production relevant environment. Resources (quantities and skill sets) identified and initial plans developed to achieve requirements for pilot line and production. Screened workforce trained in up-to-date cyber security procedures for production representative environment. | Manufacturing workforce resource requirements identified and plans developed to achieve pilot line requirements. Plans to achieve LRIP workforce requirements updated. Pilot line workforce trained in production representative environment. Screened workforce trained in up-to-date cyber security procedures for production relevant environment. | Manufacturing workforce resource requirements identified and plans developed to achieve LRIP requirements. LRIP personnel trained on pilot line where possible. Plans to achieve FRP workforce requirements initiated based on pilot line. Screened workforce trained in up-to-date cyber security procedures for a pilot line environment. | LRIP personnel requirements met. Plan to achieve FRP workforce requirements implemented. Screened workforce trained in up-to-date cyber security procedures for production. | FRP personnel requirements met. Production workforce skill sets maintained in spite of workforce attrition. Screened workforce trained in up-to-date cyber security procedures for production. | 1. Section will require additional questions as part of the question set to include the cyber focus and what constitutes a "screened" workforce. 2. Added environments to certain levels.
H - Facilities | H.1 Tooling/STE/SIE | State of the art tooling, test and inspection equipment surveyed. | Potential tooling, STE, and SIE requirements identified. | Tooling, STE, and SIE requirements for system concepts identified. Special tooling, STE, and SIE gaps identified. | Tooling/STE/SIE requirements for the preferred materiel solution considered as part of AoA. | Tooling and STE/SIE requirements identified including cyber security with supporting rationale and schedule. [APT] | Prototype tooling and STE/SIE concepts demonstrated in production relevant environment. Requirements development efforts for production tooling and STE/SIE complete. Tooling and test equipment requirements address cybersecurity vulnerabilities. [APT] | Design and development efforts for production tooling and STE/SIE initiated with STE/SIE validation plans complete. Manufacturing equipment maintenance strategy developed. Tooling and test equipment designs address cybersecurity vulnerabilities. [APT] | Tooling, test and inspection equipment proven on pilot line and additional requirements identified for LRIP. STE/SIE validated as part of pilot line validation IAW validation plan. Manufacturing equipment maintenance demonstrated on pilot line. LRIP Tooling and test equipment includes cyber vulnerability protections. [APT] | All tooling, test and inspection equipment proven in LRIP and additional requirements identified for FRP. Manufacturing equipment maintenance schedule demonstrated. STE/SIE validation maintained as necessary. New/additional tooling and test equipment required for FRP includes cyber vulnerability protections. [APT] | Proven tooling, test and inspection equipment in place to support maximum FRP. Planned equipment maintenance schedule achieved. STE/SIE validation maintained as necessary. Cyber vulnerability protections enhanced and updated. [APT]
| H.2 Facilities | Current facility capabilities and capacity surveyed. | Potential facility capabilities and capacity requirements identified. | Facility capabilities and capacity requirements and gaps for system concepts identified. In-house mfg operations cybersecurity threats and risks have been identified. [APT moved to I.1] | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA. Human factors & ergonomics and safety requirements for manufacturing (personnel, processes & equipment) identified. | Manufacturing facilities identified and plans developed to produce prototypes. Human factors & ergonomics and safety requirements for manufacturing (personnel, processes & equipment) assessed. Cybersecurity plan for in-house factory systems developed. | Manufacturing facilities identified and plans developed to produce pilot line build. Human factors & ergonomics and safety requirements for manufacturing (personnel, processes & equipment) verified in a production relevant environment. Physical and/or digital access to storage media/computers is limited to authorized personnel in the production relevant environment(?). | Manufacturing facilities identified and plans developed to produce LRIP build. Human factors & ergonomics and safety practices for manufacturing (personnel, processes & equipment) validated in a production representative environment. Planned facility layouts include security protections, physical and cyber. [APT] Physical and digital access to storage media/computers is limited to authorized personnel in the production representative environment(?). | Pilot line facilities demonstrated. Manufacturing facilities adequate to begin LRIP. Plans in place to support transition to FRP. Workplace safety is adequate. Human factors & ergonomics and safety practices for manufacturing (personnel, processes & equipment) demonstrated on a pilot line. LRIP facilities include security protections, physical and cyber. [APT] Physical and digital access to storage media/computers is limited to authorized personnel in the pilot line environment(?). | Manufacturing facilities in place and demonstrated in LRIP. Capacity plans adequate to support FRP. Human factors & ergonomics and safety practices for manufacturing (personnel, processes & equipment) demonstrated in LRIP. FRP facilities include security protections, physical and cyber. [APT] | Production facilities in place and capacity demonstrated to meet maximum FRP requirements. Human factors & ergonomics and safety requirements for manufacturing (personnel, processes & equipment) demonstrated in FRP. | Added environments based on discussion. Probably need further discussion!
I - Manufacturing Management | I.1 Manufacturing Planning & Scheduling | Manufacturing management considerations surveyed and included in early planning activities. | Manufacturing management needs assessed, analyzed and validated. | Manufacturing management requirements for system concepts identified. Potential cybersecurity vulnerabilities of the facility identified. [APT] | Manufacturing strategy for the preferred materiel solution developed, considered in the AoA, and documented in the AS. Prototype schedule risk mitigation efforts documented in the SEP. Manufacturing operations cybersecurity capabilities and cyber-vulnerabilities evaluated.[APT] | Manufacturing strategy refined based upon preferred concept. Prototype schedule risk mitigation efforts initiated. Cybersecurity requirements for ERP and Operational Technology (OT) systems identified. Cybersecurity risk management plans for internal mfg operations being implemented. **Cyber security incident handling plan developed. [APT ** = Moved from H.2] | Initial manufacturing approach developed. All system design related manufacturing events included in IMP/IMS. Manufacturing risk, and issue mitigation approach for pilot line and/or technology insertion programs defined. Planned OT systems include cybersecurity controls. **Cyber incident handling plan in place, including reporting, tracking, and corrective actions. [APT] | Initial Manufacturing Plan developed and included in IMP/IMS. Manufacturing risks and issues integrated into mitigation plans. Initial work instructions developed. Effective production control system in place to support pilot line. Factory OT systems include cybersecurity protections. Access is limited to authorized users. **Cyber incident management system in place, including reporting, tracking, and corrective actions. [APT] | Manufacturing Plan updated for LRIP. All manufacturing risks and issues identified and assessed with approved mitigation plans in place. Work instructions finalized. Effective production control system in place to support LRIP. Factory OT systems include cybersecurity protections. Access is limited to authorized users. Cyber incident management system indicates low risk for initial production. [APT] | Manufacturing plan updated for FRP. All manufacturing risks and issues managed. Effective production control system in place to support FRP. Cyber incident management system indicates no known risks and low risk for rate production. [APT] | All manufacturing risks and issues managed. Minimal cyber security incident occurance. Prompt incident identification and corrective actions minimizing impacts. [APT]
| I.2 Materials Planning | Materials planning state of the are surveyed. | Initial availability, lead time, handling and storage requirements for potential materials and components evaluated. |  | Technology development article component list developed with associated lead time estimates. | Make/buy evaluations initiated and include production considerations for pilot line, LRIP, and FRP needs. Lead times and other materials risks and issues identified. | Most material make/buy decisions complete, material risks and issues identified, and mitigation plans developed. BOM initiated. | Make/Buy decisions and BOM complete for pilot line build. Material planning systems in place for pilot line build. | Make/Buy decisions and BOM complete to support LRIP. Material planning systems proven on pilot line for LRIP build. | Make/Buy decisions and BOM complete to support FRP. Material planning systems proven in LRIP and sufficient for FRP. | Material planning systems validated on FRP build.
Bold Red = Dave K
Green = APT
Purple = Team discussion
Blue = 8/8/19 meeting
A
FRP
C
B
MDD

## Acronym List
Acronym | Meaning | Reference
AoA | Analysis of Alternatives | DoDI 5000.02
AS | Acquisition Strategy | DoDI 5000.02 and others
ASR | Alternative System Review | IEEE15288.2
BOM | Bill of Materials
CDR | Critical Design Review | IEEE15288.2
DFA | Design for Assembly
DFM | Design for Manufacturing
DMSMS | Diminishing Manufacturing Sources & Material Shortages | DMSMS Guidebook (SD-22)
EMD | Engineering and Manufacturing Development (DoD acquisition phase) | DoDI 5000.02
ESH | Environmental, Safety, and Health
FRACAS | Failure, Reporting, Analysis, and Corrective Action System
FRP | Full Rate Production | DoDI 5000.02
GFP | Government Furnished Property
IAW | In accordance with
IMP | Integrated Master Plan
IMS | Integrated Master Schedule
KC | Key Characteristic | AS6500 and AS9103
KPP | Key Performance Parameter
LRIP | Low Rate Initial Production | DoDI 5000.02
MDD | Materiel Development Decision | DoDI 5000.02
MRL | Manufacturing Readiness Level | MRL Deskbook
MS A | Milestone A (DoD Decision Point) | DoDI 5000.02
MS B | Milestone B (DoD Decision Point) | DoDI 5000.02
MS C | Milestone C (DoD Decision Point) | DoDI 5000.02
MSA | Materiel Solution Analysis (DoD acquisition phase) | DoDI 5000.02
O&S | Operations & Support (DoD acquisition phase) | DoDI 5000.02
OT | Operational Technology
PCA | Production Configuration Audit | IEEE15288.2
PDR | Preliminary Design Review | IEEE15288.2
Pre-MDD | Pre-Materiel Development Decision (DoD acquisition phase) | DoDI 5000.02
PRR | Production Readiness Review | IEEE15288.2
QMS | Quality Management System | AS9100
SEP | Systems Engineering Plan | DoDI 5000.02
SFR | System Functional Review | IEEE15288.2
SIE | Special Inspection Equipment | DoD 4275.5
SPC | Statistical Process Control
SRR | System Requirements Review | IEEE15288.2
STE | Special Test Equipment | DoD 4275.5
SVR | System Verification Review | IEEE15288.2
T&E | Test and Evaluation |  | as in Developmental (DT&E), Initial Operational (IOT&E), etc.
TMRR | Technology Maturation and Risk Reduction (DoD acquisition phase) | DoDI 5000.02
WIP | Work In Progress

## Version_2018
Version 2018 | DoD Manufacturing Readiness Levels (MRLs)
Acquisition Phase |  | Pre-Materiel Development Decision (Pre-MDD) |  |  | Materiel Solution Analysis (MSA) | Technology Maturation and Risk Reduction (TMRR) |  | Engineering & Manufacturing Development (EMD) |  | Low-Rate Initial Production (LRIP) | Full-Rate Production (FRP)
Technical Reviews |  |  |  |  | ASR | SRR/SFR | PDR | CDR | PRR/SVR | PCA
Thread | Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4 | MRL 5 | MRL 6 | MRL 7 | MRL 8 | MRL 9 | MRL 10 | NOTES
| Technology Maturity | Should be assessed at TRL 1. | Should be assessed at TRL 2. | Should be assessed at TRL 3. | Should be assessed at TRL 4. | Should be assessed at TRL 5. | Should be assessed at TRL 6. | Should be assessed at TRL 7 | Should be assessed at TRL 7 or TRL 8. | Should be assessed at TRL 8 or TRL 9. | Should be assessed at TRL 9.
A - Technology and Industrial Base | A.1 Industrial Base |  |  | Potential sources identified to address technology needs. Understand state of the art. Operational Technology (OT) Cybersecurity threats and risks in the anticipated industrial base have been identified. Potential manufacturing and quality systems OT cybersecurity capabilities and gaps identified. | Industrial base capabilities surveyed and known gaps/risks/issues identified for preferred concept, key technologies, components, and/or key processes. OT Cybersecurity threats and risks in the anticipated industrial base have been identified and risk management plans developed. Industrial Base OT cyber vulnerability and cybersecurity capabilities identified. | Industrial base capabilities assessment (including OT cybersecurity) initiated to identify potential manufacturing sources. Sole/single/foreign source vendors and vendors of technologies with potential obsolescence issues, and/or cyber vulnerabilities identified, and planning initiated to minimize risks. Industrial base OT cybersecurity vulnerabilities identified. | Industrial base capabilities assessment for MS B completed. Industrial capability in place to support manufacturing of development articles. Plans to minimize sole/single/foreign sources, and obsolescence issues, and OT cyber vulnerabilities complete. Need for sole/single/foreign sources justified. Potential alternative sources identified. | Industrial capability to support production analyzed. Sole/single/foreign sources, source stability, and obsolescence, and OT cyber vulnerability issues are assessed/ monitored. Potential alternate sources developed if necessary. | Industrial base capability assessment for MS C completed. Secure and trusted [Need to discuss what this means] Industrial capability is in place to support LRIP. Sources are available, including multi-sourcing where cost-effective or necessary to mitigate risk. | Secure and trusted [Need to discuss what this means] Industrial capability assessment for FRP has been completed and capability is in place to support start of FRP. | Secure and trusted [Need to discuss what this means] Industrial capability supports FRP and is assessed to support modifications, upgrades, surge and other potential manufacturing requirements. | 1. Added "OT" throughout 2. MRL 5 - made last part a separate sentence 3. Need to discuss meaning of "secure and trusted" - this can mean something very specific, which would not apply to all suppliers
| A.2 Manufacturing Technology Development |  | New manufacturing concepts and potential solutions identified. | Manufacturing technology concepts identified through experiments/models. | Manufacturing Science & Advanced Manufacturing Technology requirements identified. | Required manufacturing technology development efforts initiated. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions (including OT cyber security) demonstrated in a production relevant environment. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions (including OT cyber security) demonstrated in a production representative environment. | Primary manufacturing technology efforts concluding. Improvement efforts continuing. Required manufacturing technology solutions (including OT cyber security) validated on a pilot line. | Manufacturing technology process improvements (including OT cyber security) efforts initiated for FRP. | Manufacturing technology (including OT cyber security) continuous process improvements ongoing. | Added "OT" throughout; otherwise team agreed this was OK
B - Design | B.1 Producibility Program |  |  | Relevant materials/processes evaluated for manufacturability using experiments/models. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in AS key components/ technologies. | Producibility and manufacturability assessments of key technologies and components initiated. Ongoing design trades consider manufacturing processes and industrial base capability constraints. Manufacturing processes assessed for capability to be tested and verified in production. Manufacturing processes assessed for influence on O&S. | Producibility assessments and producibility trade studies (performance vs. producibility) of key technologies/components completed. Results used to shape AS, SEP, manufacturing and producibility plans, and planning for EMD or technology insertion programs. Preliminary design choices assessed against manufacturing processes and industrial base capability constraints. Producibility enhancement efforts (i.e., DFM, DFA, etc.) initiated. | Detailed producibility trade studies using knowledge of key design characteristics and related manufacturing process capability completed. Producibility enhancement efforts (i.e., DFM, DFA, etc.) ongoing for optimized integrated system. Manufacturing processes re-assessed as needed for capability to be tested and verified. Manufacturing processes re-assessed as needed for potential influence on O&S. | Producibility improvements implemented on system. Known producibility risks and issues managed for LRIP. | Prior producibility improvements analyzed for effectiveness during LRIP. Producibility risks and issues discovered in LRIP managed for FRP. | Design producibility improvements demonstrated in FRP. Process producibility improvements ongoing. All modifications, upgrades, DMSMS and other changes assessed for producibility. | No new criteria
| B.2 Design Maturity | Manufacturing research opportunities identified. | Applications defined. Broad performance goals identified that may drive manufacturing options. | Top level performance requirements defined. Trade-offs in design options assessed based on experiments. Product lifecycle and technical requirements evaluated. | SEP and T&E Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial KPPs identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints, and manufacturing capabilities identified for preferred systems concept. | Lower level performance requirements sufficient to proceed to preliminary design. All enabling/critical technologies and components identified and the product lifecycle considered. Evaluation of the design for KCs initiated. Product data required for prototype component manufacturing released. | System allocated baseline established. Product requirements and features are well enough defined to support PDR. Product data essential for subsystem/ system prototyping has been released, and all enabling/critical components have been prototyped. Preliminary KCs for the design identified and mitigation plans initiated. | Product design and features are well enough defined to support CDR, even though design change traffic may be significant. All product data essential for component manufacturing released. Potential KC risks and issues identified with mitigation plans in place. | Detailed design of product features and interfaces completed. All product data essential for system manufacturing released. Design change traffic does not significantly impact LRIP. KCs are attainable based upon pilot line demonstrations. | Major product design features and configuration are stable. System design has been validated through operational testing of LRIP items. PCA or equivalent complete as necessary. Design change traffic is limited. All KCs are controlled in LRIP to appropriate quality levels. | Product design is stable. Design changes are few and generally limited to those required for continuous improvement or in reaction to obsolescence. All KCs are controlled in FRP to appropriate quality levels. | No new criteria
C - Cost & Funding | C.1 Production Cost Knowledge (Cost modeling) |  | Cost model approach defined. | Initial cost targets and risks identified. High level process chart model developed. Technology cost models developed for new process steps and materials based on experiments. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified. | Prototype components produced in a production relevant environment, or simulations drive end-to-end cost models. Cost model includes materials, labor, equipment, tooling/STE/SIE, setup, yield/scrap/rework, WIP, and capability/capacity constraints. | Cost model updated with design requirements, material specifications, tolerances, IMS, results of system/subsystem simulations and production relevant prototype demonstrations. | Cost model updated with the results of systems/sub-systems produced in a production representative environment, production plant layout and design, and obsolescence solutions. | Cost model updated with results of pilot line build. | FRP cost model updated with result of LRIP build. | Cost model validated against actual FRP cost. | No new criteria
| C.2 Cost Analysis | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory). | Producibility cost risks and issues assessed. Initial cost model supports AoA and ASR. | Costs analyzed using prototype component actuals to ensure target costs are achievable. Decisions regarding design choices, make/buy, capacity, process capability, sources, quality, KCs, yield/rate, and variability influenced by cost models. | Costs analyzed using prototype system/sub-system actuals to ensure target costs are achievable. Cost targets allocated to subsystems. Cost reduction and avoidance strategies developed. Manufacturing cost drivers for "Should-Cost" model provided. | Manufacturing costs rolled up to system/sub-system level and tracked against targets. Detailed trade studies and engineering change requests supported by cost estimates. Cost reduction and avoidance strategies underway. Manufacturing cost drivers for "Should-Cost" model updated. | Costs analyzed using pilot line actuals to ensure target costs are achievable. Manufacturing cost analysis supports proposed changes to requirements or configuration. Cost reduction initiatives ongoing. Manufacturing cost drivers for "Should-Cost" model updated. | LRIP cost goals met and learning curves analyzed with actual data. Cost reduction initiatives ongoing. Touch labor efficiency analyzed to meet production rates and elements of inefficiency are identified with plans in place for reduction. | FRP cost goals met. Cost reduction initiatives ongoing. | No new criteria
| C.3 Manufacturing Investment Budget | Potential investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risks and issues understood with approved mitigation plans in place. | Program has updated budget estimate for reaching MRL 6 by MS B. All outstanding MRL 5 risks and issues understood with approved mitigation plans in place. | Program has reasonable budget estimate for reaching MRL 8 by MS C. Estimate includes capital investment for production-representative equipment by CDR and pilot line equipment by MS C. All outstanding MRL 6 risks and issues understood with approved mitigation plans in place. | Program has updated budget estimate for reaching MRL 8 by MS C. All outstanding MRL 7 risks and issues understood with approved mitigation plans in place. | Program has reasonable budget estimate for reaching MRL 9 by the FRP decision point. Estimate includes investment for LRIP and FRP. All outstanding MRL 8 risks and issues understood with approved mitigation plans in place. | Program has reasonable budget estimate for FRP. All outstanding MRL 9 risks and issues understood with approved mitigation plans in place. | Production budgets sufficient for production at required rates and schedule to support funded program. | No new criteria
D - Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | D.1 Maturity | Material properties identified for research. | Material properties and characteristics predicted. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials produced in a laboratory environment. | Materials manufactured or produced in a prototype environment (may be in a similar application/program). Maturation efforts in place to address new material production risks for technology demonstration. | Material maturity verified through technology demonstration articles. Preliminary material specifications in place. Material properties adequately characterized. | Material maturity sufficient for pilot line build. Material specifications approved. | Materials proven and validated during EMD as adequate to support LRIP. Material specifications stable. | Materials controlled to specifications in LRIP. Materials proven and validated as adequate to support FRP. | Materials controlled to specifications in FRP. | No new criteria
| D.2 Availability |  | Material availability assessed. | Material scale-up issues identified. | Projected lead times identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated. | Availability risks and issues addressed for prototype build. Significant material risks identified for all materials. Planning initiated to address scale-up issues. | Availability risks and issues addressed to meet EMD build. Long-lead items identified. Potential obsolescence issues identified. Components assessed for future DMSMS risk. | Availability risks and issues addressed to meet LRIP builds. Long lead procurements identified and mitigated. Obsolescence plan in place. DMSMS mitigation strategies for components in place. | Availability risks and issues managed for LRIP. Long lead procurement initiated for LRIP. Availability issues addressed to meet FRP builds. | Long lead procurement initiated for FRP. Availability risks and issues managed for FRP. | All material availability risks and issues managed. | No new criteria
| D.3 Supply Chain Management |  |  | Initial assessment of potential supply chain capability. Potential OT cybersecurity capabilities and cyber-vulnerabilities identified. | Survey for potential supply chain sources completed. OT Cybersecurity capabilities and cyber-vulnerabilities evaluated. | Potential supply chain sources identified and evaluated as able to support prototype build. Supply chain OT cyber security and vulnerability risks and issues assessed with mitigation/incident plans initiated. [Is this a new plan we need to define? Or is it an MMP?] | Lifecycle Supply Chain requirements updated. Critical suppliers list updated. Supply chain plans in place (e.g. teaming agreements, etc.) supporting an EMD contract award. Supply chain OT cyber security and vulnerability risk mitigation plans developed. [Is this a new plan? Or MMP?] Cyber incident handling system developed. | Effective supply chain management processes defined, documented, and in place. Plan developed for predictive indicators. Assessment of critical first tier supply chain completed (i.e., capability, capacity, etc.). Supply chain OT cyber security and vulnerability risk mitigation plans implemented. [Are these new plans or MMPs?] Cyber incident management system including reporting, tracking, and corrective actions, in place. | Assessment of critical second and lower tier supply chain completed. Robust requirements flow down processes in place and verified. Supplier compliance with program requirements and changes validated. Plan for predictive indicators for use in production updated. Supply chain adequate to support LRIP. Supply Chain Cyber OT incident management system indicates low acceptable risk for initial production. | Long term agreements in place where practical. Prime's supplier management metrics (including thresholds and goals) in place and used to manage risks. Predictive indicators to manage suppliers in place. Supply chain is stable and adequate to support FRP. Supply Chain OT Cyber incident management system indicates no known risks and low acceptable risk for rate production. | Supply chain proven and supports FRP requirements. Minimal OT cyber security incident occurance. Prompt incident identification and corrective actions minimizing impacts. OT Cyber incidents are identified and corrected prior to impacting production. | 1. Added "OT" throughout 2. Need to discuss: Are thses risk mitigation plans the same as MMPs? Or something different that we need to define? 3. Changed "low risk" to "acceptable risk" 4. Reworded MRL 10 to avoid unclear timing of "prompt"
| D.4 Special Handling (i.e. GFP, shelf life, security, hazardous materials, storage environment, ESH, etc.) |  | Initial evaluation of potential regulatory requirements and special handling concerns. | ESH compliance risk identified. List of hazardous materials identified and alternatives evaluated. Special handling procedures applied in the lab. Special handling concerns assessed. | ESH compliance risk mitigated in lab environment. List of hazardous materials updated and alternatives assessed. Special handling procedures applied and disposal procedures evaluated. Special handling requirements (including security, physical and cyber)[APT] identified and analyzed. | ESH requirements and special handling procedures applied in production relevant environment. Special handling (including security, physical and cyber) [APT] requirement gaps identified. New special handling processes demonstrated in lab environment. | ESH requirements addressed and documented. Special handling procedures (including security, physical and cyber)[APT] demonstrated in production relevant environment. Plans to address special handling requirement gaps, risks, and issues complete. Manufacturing assessed for material storage and waste handling risks. | ESH compliance demonstrated in production representative environment. Special handling procedures (including security, physical and cyber)[APT] applied in production representative environment. Special handling procedures developed and annotated on work instructions for pilot line. Hazardous material storage and disposal plan in place for the pilot line. | ESH compliance demonstrated in pilot line production. Special handling procedures (including security, physical and cyber)[APT] applied in pilot line environment and demonstrated in EMD or technology insertion programs. Special handling risks and issues managed for LRIP. All work instructions contain special handling provisions as required. Hazardous material storage and disposal plan evaluated and in place for LRIP. | ESH compliance demonstrated in LRIP. Special handling (including security, physical and cyber)[APT], and hazardous material storage and disposal procedures demonstrated in LRIP environment. Special handling, and hazardous material storage and disposal risks and issues managed for FRP. | ESH compliance demonstrated in FRP. Special handling (including security, physical and cyber)[APT] and hazardous material storage and disposal procedures effectively implemented in FRP. | Security is already included under Special Handling. This includes both physical and cyber.
E - Process Capability & Control | E.1 Modeling & Simulation (Product & Process) |  | Initial models developed, if applicable. | Identification of proposed manufacturing concepts or producibility needs based on high-level process flow chart models. | Production modeling & simulation approaches for process or product are identified. | Initial modeling & simulations (product or process) developed at the component level and used to determine constraints. | Initial modeling & simulations developed at the sub-system or system level, and used to determine system constraints. | Modeling & simulations used to determine system constraints and to identify improvement opportunities. | Modeling & simulations verified by pilot line build. Results used to improve process and demonstrate that LRIP requirements can be met. | Modeling & simulations verified by LRIP build, assist in management of LRIP, and demonstrate that FRP requirements can be met. | Modeling & simulations verified by FRP build. Production simulation models used as tools to assist in management of FRP.
| E.2 Manufacturing Process Maturity |  | Identification of material and/or process approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Survey to determine the current state of critical processes completed. | Process Maturity assessed on similar processes in production. Process capability requirements identified for pilot line, LRIP and FRP. | Manufacturing processes demonstrated in production relevant environment. Collection or estimation of process capability data from prototype build and refinement of process capability requirements initiated. | Manufacturing processes demonstrated in a production representative environment. Collection and/or estimation of process capability data and refinement of process capability requirements ongoing. | Manufacturing processes for LRIP verified on a pilot line. Process Capability data from pilot line meets target. Process capability requirements for LRIP and FRP refined based upon pilot line data. | Manufacturing processes are stable, adequately controlled, capable, and have achieved program LRIP objectives. Variability experiments conducted to show FRP impact and potential for continuous improvement. | Manufacturing processes are stable, adequately controlled, capable, and have achieved program FRP objectives. | Should this Sub-Thread include interoperability?
| E.3 Process Yields and Rates |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rate assessments on proposed/similar processes complete and applied within the AoA. | Target yields and rates established for pilot line, LRIP, and FRP. Yield and rate issues identified. Improvement plans developed/initiated. | Yields and rates from production relevant environment evaluated against targets and the results feed improvement plan. | Yields and rates from production representative environment evaluated against pilot line targets and the results feed improvement plans. | Pilot line targets achieved. Yields and rates required to begin LRIP refined using pilot line results. Improvement plans ongoing and updated. | LRIP yield and rate targets achieved. Yields and rates required to begin FRP refined using LRIP results. Yield improvements on-going. | FRP yield and rate targets achieved. Yield improvements on-going.
F - Quality | F.1 Quality Management |  |  |  | Quality strategy identified as part of the AS and included in SEP. | Quality strategy updated to reflect KC identification activities. Cyber security incident handling plan developed. | Initial Quality Plan and QMS are in place. Quality risks, issues, and metrics have been identified and improvement plans initiated. Cyber incident handling plan in place, including reporting, tracking, and corrective actions. | Quality targets established. QMS elements (i.e., control of nonconforming material, corrective action, etc.) meet requirements of appropriate industry standards. Program-specific Quality Program Plan developed. Cyber incident handling plan in place, including reporting, tracking, and corrective actions. | Program-specific Quality Program Plan established. Program Quality Manager assigned. Quality targets assessed against pilot line, results feed continuous quality improvements. Trends in cybersecurity incidents indicate no significant risk for production. | Quality targets verified on LRIP line. Continuous quality improvement on-going. Management review of Quality measures conducted on regular basis and appropriate actions taken. Trends in cybersecurity incidents indicate no significant risk for full rate production. | Quality targets verified on FRP line. Continuous quality improvement on-going. Statistical controls applied where appropriate. Minimal cybersecurity incidents occur. Incidents that do occur have effective corrective actions implemented.
| F.2 Product Quality |  |  |  | Product inspection and acceptance testing strategy identified as part of the AS and included in SEP. | Roles and responsibilities identified for acceptance test procedures, in-process and final inspections, and statistical process controls for prototype units. | KC management approach defined. Initial requirements identified for acceptance test procedures and in-process and final inspection requirements for EMD units. Appropriate inspection and acceptance test procedures identified for prototype units. | Quality data from the production representative environment collected and analyzed and results used to shape improvement plans. Control plans completed for management of KCs. Test and Inspection plans being developed for EMD units. | KCs managed. Measurement procedures and controls in place (e.g. SPC, FRACAS, audits, customer satisfaction, etc.). Pilot line data meets capability requirements for all KCs. Test and Inspection plans complete and validated for production units. | Data from LRIP demonstrates production processes, for all KCs and other manufacturing processes critical to quality, are capable and under control for FRP. | KCs controlled at rate. Results achieve targeted statistical level on all KCs. Results reflect continuous improvement.
| F.3 Supplier Quality/ Management |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management. | Supply base quality capabilities and risks identified, including subtier supplier quality management. | Supply base quality improvement initiatives identified addressing supplier QMS shortfalls, including subtier supplier quality management. | Key supplier QMSs meet appropriate industry standards. Supplier quality data from production representative units collected and analyzed. Strategy for audits of critical supplier processes outlined. | Supplier program-specific QMSs adequate. Supplier products qualification testing and first article inspection completed. Acceptance testing of supplier products adequate to begin LRIP. Plan for subcontractor process audits in place and implemented by prime contractor. | Supplier quality management of KCs and other critical manufacturing processes demonstrates capability and control for FRP. Acceptance testing of supplier products reflects control of quality adequate to begin FRP. Subcontractor quality audits performed as necessary to ensure subcontractor specification compliance. | Supplier quality data reflects adequate management of KCs and control of critical manufacturing processes, including quality management down to subtier suppliers. Results achieve high statistical level (e.g., 6-sigma) on all critical dimensions. Subcontractor quality audits performed as necessary to ensure subcontractor specification compliance.
G - Manufacturing Workforce (Engineering & Production) | G.1 Manufacturing Workforce (Engineering & Production) |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Availability of process development workforce for TMRR Phase determined. | Skill sets identified and plans developed to meet prototype and production needs. Special skills certification and training requirements established. Cybersecurity training needs identified and plan developed for mfg workforce. Special skills, certifications, cyber security, etc. training requirements established. Screened workforce trained in cyber security. [APT] | Manufacturing workforce skills available for the production relevant environment. Resources (quantities and skill sets) identified and initial plans developed to achieve requirements for pilot line and production. Cybersecurity training plan developed for manufacturing workforce. Systems and functions limited to authorized users. Workforce trained in cyber security procedures. Screened workforce trained in up-to-date cyber security procedures for production representative environment. [APT] | Manufacturing workforce resource requirements identified and plans developed to achieve pilot line requirements. Plans to achieve LRIP workforce requirements updated. Pilot line workforce trained in production representative environment. Workforce trained in cyber security procedures. Factory IT systems and functions limited to authorized users. Screened workforce trained in up-to-date cyber security procedures for production relevant environment. [APT] | Manufacturing workforce resource requirements identified and plans developed to achieve LRIP requirements. LRIP personnel trained on pilot line where possible. Plans to achieve FRP workforce requirements initiated based on pilot line. Workforce trained in cyber security procedures. Factory IT systems and functions limited to authorized users. Screened workforce trained in up-to-date cyber security procedures for a pilot line environment. [APT] | LRIP personnel requirements met. Plan to achieve FRP workforce requirements implemented. Workforce cybersecurity training plan ensures new hires for full rate production are trained and screened prior to allowing access to IT systems and functions. Screened workforce trained in up-to-date cyber security procedures for production. [APT] | FRP personnel requirements met. Production workforce skill sets maintained in spite of workforce attrition. Screened workforce trained in up-to-date cyber security procedures for production. [APT] | 1. Section will require additional questions as part of the question set to include the cyber focus and what constitutes a "screened" workforce. 2. Added environments to certain levels.
H - Facilities | H.1 Tooling/STE/SIE |  |  |  | Tooling/STE/SIE requirements are considered as part of AoA. | Tooling and STE/SIE requirements identified including cyber security with supporting rationale and schedule. [APT] | Prototype tooling and STE/SIE concepts demonstrated in production relevant environment. Requirements development efforts for production tooling and STE/SIE complete. Cybersecurity requirements identified for tooling and test equipment. Tooling and test equipment requirements address cybersecurity vulnerabilities. [APT] | Design and development efforts for production tooling and STE/SIE initiated with STE/SIE validation plans complete. Manufacturing equipment maintenance strategy developed. Tooling and test equipment designs include cybersecurity protections. Tooling and test equipment designs address cybersecurity vulnerabilities. [APT] | Tooling, test and inspection equipment proven on pilot line and additional requirements identified for LRIP. STE/SIE validated as part of pilot line validation IAW validation plan. Manufacturing equipment maintenance demonstrated on pilot line. LRIP tooling and test equipment include cybersecurity protections. LRIP Tooling and test equipment includes cyber vulnerability protections. [APT] | All tooling, test and inspection equipment proven in LRIP and additional requirements identified for FRP. Manufacturing equipment maintenance schedule demonstrated. STE/SIE validation maintained as necessary. New/additional tooling and test equipment required for full rate production include cybersecurity protections. New/additional tooling and test equipment required for FRP includes cyber vulnerability protections. [APT] | Proven tooling, test and inspection equipment in place to support maximum FRP. Planned equipment maintenance schedule achieved. STE/SIE validation maintained as necessary. Cyber vulnerability protections enhanced and updated. [APT]
| H.2 Facilities Added environments based on discussion. Probably need further discussion! |  |  | Specialized facility requirements/needs identified. In-house mfg operations cybersecurity threats and risks have been identified. [APT moved to I.1] | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA. Human factors & ergonomics and safety requirements for manufacturing (personnel, processes & equipment) identified. In-house mfg operations cybersecurity threats and risks in-house have been identified. Risk management plans developed to address cybersecurity risks. | Manufacturing facilities identified and plans developed to produce prototypes. Human factors & ergonomics and safety requirements for manufacturing (personnel, processes & equipment) assessed. Cybersecurity risk management plans for internal mfg operations being implemented. ****Cyber security incident handling plan developed. [**** = Moved from Quality Management] Cybersecurity plan for in-house factory systems developed. | Manufacturing facilities identified and plans developed to produce pilot line build. Human factors & ergonomics and safety requirements for manufacturing (personnel, processes & equipment) verified in a production relevant environment. Production relevant environment for prototypes and technology demonstrators include secure factory IT systems. [APT covered under D.4] Physical and/or digital access to storage media/computers is limited to authorized personnel in the production relevant environment(?). ****Cyber incident handling plan in place, including reporting, tracking, and corrective actions. | Manufacturing facilities identified and plans developed to produce LRIP build. Human factors & ergonomics and safety practices for manufacturing (personnel, processes & equipment) validated in a production representative environment. Planned facility layouts include cybersecurity protections, physical and cyber. [APT] Physical and digital access to storage media/computers is limited to authorized personnel in the production representative environment(?). ****Cyber incident handling plan in place, including reporting, tracking, and corrective actions. | Pilot line facilities demonstrated. Manufacturing facilities adequate to begin LRIP. Plans in place to support transition to FRP. Workplace safety is adequate. Human factors & ergonomics and safety practices for manufacturing (personnel, processes & equipment) demonstrated on a pilot line. LRIP facilities include cybersecurity protections, physical and cyber. [APT] Physical and digital access to storage media/computers is limited to authorized personnel in the pilot line environment(?). ****Trends in cybersecurity incidents indicate no significant risk for production. | Manufacturing facilities in place and demonstrated in LRIP. Capacity plans adequate to support FRP. Human factors & ergonomics and safety practices for manufacturing (personnel, processes & equipment) demonstrated in LRIP. FRP facilities include cybersecurity protections, physical and cyber. [APT] ****Trends in cybersecurity incidents indicate no significant risk for full rate production. | Production facilities in place and capacity demonstrated to meet maximum FRP requirements. Human factors & ergonomics and safety requirements for manufacturing (personnel, processes & equipment) demonstrated in FRP. ****Minimal cybersecurity incidents occur. Incidents that do occur have effective corrective actions implemented. | Added environments based on discussion. Probably need further discussion!
I - Manufacturing Management | I.1 Manufacturing Planning & Scheduling |  |  | Potential cybersecurity vulnerabilities of the facility identified. [APT] | Manufacturing strategy developed and integrated with the AS. Prototype schedule risk mitigation efforts incorporated into the AS. Manufacturing operations cybersecurity capabilities and cyber-vulnerabilities evaluated.[APT] | Manufacturing strategy refined based upon preferred concept. Prototype schedule risk mitigation efforts initiated. Cybersecurity requirements for ERP and Operational Technology (OT) systems identified. Cybersecurity risk management plans for internal mfg operations being implemented. **Cyber security incident handling plan developed. [APT ** = Moved from H.2] | Initial manufacturing approach developed. All system design related manufacturing events included in IMP/IMS. Manufacturing risk, and issue mitigation approach for pilot line and/or technology insertion programs defined. Planned OT systems include cybersecurity controls. **Cyber incident handling plan in place, including reporting, tracking, and corrective actions. [APT] | Initial Manufacturing Plan developed and included in IMP/IMS. Manufacturing risks and issues integrated into mitigation plans. Initial work instructions developed. Effective production control system in place to support pilot line. Factory OT systems include cybersecurity protections. Access is limited to authorized users. **Cyber incident management system in place, including reporting, tracking, and corrective actions. [APT] | Manufacturing Plan updated for LRIP. All manufacturing risks and issues identified and assessed with approved mitigation plans in place. Work instructions finalized. Effective production control system in place to support LRIP. Factory OT systems include cybersecurity protections. Access is limited to authorized users. Cyber incident management system indicates low risk for initial production. [APT] | Manufacturing plan updated for FRP. All manufacturing risks and issues managed. Effective production control system in place to support FRP. Cyber incident management system indicates no known risks and low risk for rate production. [APT] | All manufacturing risks and issues managed. Minimal cyber security incident occurance. Prompt incident identification and corrective actions minimizing impacts. [APT]
| I.2 Materials Planning |  |  |  | Technology development article component list developed with associated lead time estimates. | Make/buy evaluations initiated and include production considerations for pilot line, LRIP, and FRP needs. Lead times and other materials risks and issues identified. | Most material make/buy decisions complete, material risks and issues identified, and mitigation plans developed. BOM initiated. | Make/Buy decisions and BOM complete for pilot line build. Material planning systems in place for pilot line build. | Make/Buy decisions and BOM complete to support LRIP. Material planning systems proven on pilot line for LRIP build. | Make/Buy decisions and BOM complete to support FRP. Material planning systems proven in LRIP and sufficient for FRP. | Material planning systems validated on FRP build.
Red = Dave K
Green = APT
Purple = Team discussion
Blue = 8/8/19 meeting
A
FRP
C
B
MDD